## Sheet1
Annex 1
| ID | Goal set out in the Strategic Plan | Indicators | Development project | Deadline | Owner | Project manager
Research and development
Research activities Research activities | 1 | At TalTech, high-level research is conducted, which serves as the basis for applications, studies and research-intensive innovation. | 1. Annual number of Q1 category articles per an academic staff member with a PhD. 2. Number and satisfaction of those who have completed the mentoring programme (the top researchers and junior researchers who have built a mentor/mentee relationship). 3. Increase in the number of joint publications and projects (1+ department). 4. Increase in the number of joint publications and projects in strategic focus areas (of Estonian Research and Development, Innovation and Entrepreneurship Development Plan). 5. Number of researchers co-supervising PhD theses. 6. Supervision efficiency (phD). | Best practice sharing program | 2025 | Maarja Kruusmaa | Maia-Liisa Anton, Tea Trahov, Mihkel Läänelaid
Our research results are published in high-level scientific publications and the doctoral theses defended at the university are predominantly based on such research.
We support sustainable, responsible and high-level research groups that make a significant contribution to teaching and serving society.
| 2 | To this end, we further develop the university's internal funding model, which would mitigate the risks of ambitious and entrepreneurial research groups and promote cooperation between research groups in the university's strategic research areas. | 1. The indicator is under development. | Developing focus topics and linking them to university management decisions | 2025 | Maarja Kruusmaa | Maarja Kruusmaa
| 3 | We improve the level and effectiveness of doctoral studies and take into account the needs of Estonian economy in doctoral studies. | 1. Number of defended doctoral theses per year. 2. Number of high-level publications per doctoral thesis. 3. Connection of doctoral theses with industry and business. 4. Supervision and graduation efficiency - nominal duration of study +1 year 5. Satisfaction of PhD students with supervision. 6. Number of industrial PhD students. 7. Number of supervisors from outside the university. 8. Number of foreign PhD students who have acquired proficiency in the Estonian language at A1 level. | Improving the quality of doctoral studies | 2025 | Maarja Kruusmaa | Kaire Kaljuvee
Our research results are published in high-level scientific publications and the doctoral theses defended at the university are predominantly based on such research.
| 4 | We will increase the university's competitive research funding and assist research groups in applying for funding, in particular in the university's strategic research areas. | 1. The amount of launched R&D projects per FTE of an academic staff member with a PhD (thousand euros). 2. Diversity of projects by measure. 3. Number and volume of project proposals submitted in cooperation with companies - a company as a customer or partner. 4. Number, volume and success rate of project proposals. 5. Number of project proposals prepared with the participation of the project writers team. 6. Success rate of proposals prepared with the participation of the Research Administration Office (above the threshold, funded). 7. Satisfaction of researchers who have used the counselling service. 8. Satisfaction of academic staff and project managers with the project support services provided by the Research Administration Office. 9. Number of applicants who have submitted successful project proposals. 10. Number of successful project proposals (threshold, funding). 11. Ineligible costs and recoveries and their share of the volume. | ALPHA: user-centric management of R&D projects | 2024 | Maarja Kruusmaa | Maia-Liisa Anton, Maarja Parve, Siim Läänelaid, Marika Lunden
|  | To this end, we further develop the university's internal funding model, which will mitigate the risks of ambitious and entrepreneurial research groups and promote cooperation between research groups in the university's strategic research areas. |  | Development of a comprehensive support service for R&D projects | 2023 | Maarja Kruusmaa | Maia-Liisa Anton, Maarja Parve, Siim Läänelaid, Marika Lunden
|  | We support outstanding young researchers to help them quickly gain independence and develop as members of our university family. |  | Creating and launching a grant fund | 2022 | Maarja Kruusmaa | Mihkel Läänelaid, Maia-Liisa Anton
| 5 | We will integrate more closely with and are involved in shaping the European Research Area. | 1. Participation of TalTech members in the policy-making process (working groups, councils, professional associations). 2. Applying TalTech knowledge in policy making. 3. Awareness of policy makers and their cooperation with TalTech members. 4. Reputation and visibility, including international. | Establishment of the R&D policy-making unit | 2023 | Maarja Kruusmaa | Aleksander Vukkert, Maia-Liisa Anton, Kaja Kuivjõgi
| 6 | Tallinn University of Technology conducts open research and provides open education. Study materials and research results are available to business partners, school students and the public. | 1. Number of databases in the repository 2. Satisfaction with the services provided. 3. Number of external requests to use data (HPC). | Development of data management support service | 2023 | Maarja Kruusmaa | Tõnis Liibek, Lauri Anton
Support services are developed in cooperation with the academic staff, mutually acknowledging each other's contribution and understanding each other's expectations.
| 7 | At TalTech, high-level research is conducted, which serves as the basis for applications, studies and research-intensive innovation. | 1. Infrastructure occupancy rate. 2. Connection of infrastructure with publications. 2. Cross-use of infrastructure. | Development of a sustainable (cross) use and funding model for research laboratories | 2025 | Maarja Kruusmaa | Kristel Rauk
| 8 | The university shall provide seamless, efficient and cost-effective support services with an aim to support and better integrate high-quality studies, research and innovation. | 1. Number of users (visitors and online environments). 2. Number of publications. 3. Increase of the areas open 24/7. 4. User satisfaction with database services and library services and environment. | Implementation of the library of the future | 2025 | Maarja Kruusmaa | Tõnis Liibek
| 9 | We value our university's history and the members of the university staff who have helped to preserve and develop engineering and technology education. | 1. Number of exhibitions. 2. Number and structure of visitors. 3. Visitor satisfaction. | Creating new major exhibitions | 2023 | Maarja Kruusmaa | Tõnis Liibek
Study activities
Study activities Study activities | 10 | All our study programmes include project and problem-based learning and and successful entrepreneurs, managers, and top professionals contribute to student education. | 1. Graduation efficiency. 2. Graduates’ satisfaction with the study programme. 3. Average salary (coefficient) of master's graduates. 4. 8 new auditoriums suitable for conducting project-based learning. 5. The number of students admitted per main speciality corresponds to the minimum set out in the Curriculum Statute. 6. The graduation efficiency of study programmes is at least 60%. 7. The share of professors among teaching staff conducting studies in each main speciality of master’s studies is at least 20%. 8. The share of academic staff with a PhD among teaching staff conducting studies in master’s studies is 75%. 9. The share of academic staff with a PhD among teaching staff conducting studies in bachelor’s studies is 50%. 10. The share of academic staff with a PhD among teaching staff conducting studies in integrated studies is 60%. 11. The share of academic staff with a PhD among teaching staff conducting studies in professional higher education studies is 35%. | Introduction of problem- and project-based learning | 2022 | Hendrik Voll | Betra Leesment
| 11 | Our graduates are able to solve real-life problems with their evidence-based mindset, practical engineering skills, good self-management and cooperation skills and entrepreneurial spirit. They are ready to take responsibility for the development of the Estonian economy. |  | Complex indicators of study programme quality and monitoring system | 2021 | Hendrik Voll | Laura Mere
| 12 | To this end, we develop teaching and learning at Tallinn University of Technology in cooperation with the stakeholders so that our graduates acquire modern, high-quality professional education based on the natural and social sciences, embrace the university’s values. | 1. Graduation efficiency. 2. Share of courses for which student ratings are above 4.2 points. 3. Graduates’ satisfaction with the study programme. 4. A didactics centre in each department. | Development of a teacher training program | 2021 | Hendrik Voll | Maria Torm
| 13 | To this end, we develop teaching and learning at Tallinn University of Technology in cooperation with the stakeholders so that our graduates acquire modern, high-quality professional education based on the natural and social sciences, embrace the university’s values... |  | Launching of school-based didactics and pedagogy centers | 2023 | Hendrik Voll | Maria Torm, Kersti Matiisen
| 14 | We encourage the academic staff to communicate with the public and are able to explain our research results to the general public and raise interest in science and engineering education. | 1. Number of students who have participated in TalTech courses. 2. Percentage of participants in courses and electives who have commenced studies at TalTech. 3. Admission of students who have shown good results at subject proficiency olymiads. 4. Percentage of students whose result of the state examination in broad mathematics is 90-100 points. | Programme of upper secondary school electives for partner schools | 2025 | Hendrik Voll | Hanno Tomberg
| 15 | We introduce new forms of continuing education and lifelong learning based on the learners’ and labour market needs. | 1. Number of participants in continuing education and school student courses 2. Number of continuing education study programmes and courses 3. Number of new study programmes 4. Number of study programmes with e-support 5. Continuing education satisfaction index (from 2023) | Harmonizing the level and quality of continuing education studies | 2023 | Hendrik Voll | Hanno Tomberg
| 16 | The university's environments, both physical and virtual, are convenient and sustainable. | 1. Number of e-courses that have received the quality label of the Estonian Quality Agency for Higher and Vocational Education (EKKA). 2. Number of TalTechDigital online courses. 3. Students’ satisfaction with 2nd and 3rd level e-courses. | Improving the quality of e-learning and e-support | 2025 | Hendrik Voll | Liisi Järve
| 17 | The university's environments, both physical and virtual, are convenient and sustainable. | 1. 6 high-level auditoriums for hybrid learning. 2. 19 auditoriums with two-way video communication systems. 3. Minimum hybrid learning capacity in all the public auditoriums (140). | Improving hybrid learning capacities in classrooms | 2025 | Hendrik Voll | Liisi Järve
| 18 | The university's environments, both physical and virtual, are convenient and sustainable. | 1. Satisfaction of the employee target groups (teaching staff, schools, departments, support units) with the study information system. 2. Student feedback (assessment of experience in using the study information system). | Development of a digital environment supporting degree studies | 2025 | Hendrik Voll | Ülle Laur
| 19 | To this end, together with partners from the EuroTech Universities Alliance, we lay a foundation for the Europe's most influential centre of engineering and economics education. | 1. Share of credit points received in foreign universities in the total amount of credit points. 2. Share of credit points received in Euroteq universities in the total amount of credit points. 3. Share of students participating in mobility in the total number of students. 4. Share of students participating in mobility in Euroteq universities in the total number of students. | EuroTeQ | 2023 | Hendrik Voll | Aet Michelson
Business activities
Business activities | 20 | Tallinn University of Technology is an important engine of the Estonian economy. | 1. Income from R&D contracts and services (million euros). 2. Income from laboratory services (million euros). 3. Total number of customers. 4. Number of primary customers. 5. Number of framework agreements. 6. Number of queries. 7. Number of tenders, success rate of tenders. | Optimization and quality improvement of business cooperation support processes (incl. ALPHA) | 2022 | Sven Illing | Sven Illing, Reet Pärgmäe
| 21 | Tallinn University of Technology is an important engine of the Estonian economy. | 1. Number of enterprises participating in the digital maturity assessment. 2. Number of employees in companies who have participated in digital awareness trainings. 3. Number of demo projects carried out with enterprises. 4. Number of innovation projects submitted to the Innovation Radar. | Supporting digital maturity and the uptake of new technologies by SMEs (EDIH) | 2025 (2028) | Sven Illing | Kirke Maar
We enhance our international reputation through cooperation with top universities and research-intensive companies in the world.
| 22 | Tallinn University of Technology conducts open research and provides open education. Study materials and research results are available to business partners, school students and the public. | 1. Number of laboratories the data of which have been updated in ETIS. 2. Share of laboratories with updated data in the total amount of laboratories (we will provide information regarding the past in the form: updated/total number). 3. Number of audited and updated laboratory services in the Estonian Research Information System ETIS. 4. Number of accredited laboratories. | Updating research infrastructure data and improving access to laboratory services | 2022 | Sven Illing | Katre Eljas-Taal
| 23 | The university's spin-offs are highly regarded internationally. | 1. Number of student teams who have received advisory services. 2. Number of researcher teams who have received advisory services. 3. Number of students participating in the programmes per year. 4. Number of researchers (incl. engineers) participating in the programmes per year. 5. Number of spin-offs established. 6. Total number of spin-offs by the end of the year. 7. Volume of investments involved in spin-offs (EUR). 8. Number of other start-ups established 9. Number of start-ups in which the alumni hold shares | Establishing a support system for the commercialization of branches, start-ups and IOs | 2023 | Sven Illing | Kaisa Hansen
| 24 | We will pay more attention to the creation of intellectual property. | 1. Number of patents per year. 2. Total number of patents in force at the end of the year. 3. Number of filed patent applications. 4. Number of trainings. | Optimizing the patent portfolio and improving support for and raising awareness on IO law enforcement | 2022 | Sven Illing | Mart Koppel
We protect our intellectual property if it helps harness scientific developments to build a better society.
| 25 | Tallinn University of Technology is an important engine of Estonian economy. | 1. Number of partners who have been offered industrial property rights. 2. Number of licence agreements. 3. Revenue from sale of objects of industrial property rights (euros). | Increasing the ability to find business partners | 2022 | Sven Illing | Mart Koppel
| 26 | Alumni and today’s students are our greatest asset and we welcome them back to the university to develop themselves, share experiences and cooperate. | 1. Volume of scholarships by value propositions (EUR). 2. Number of scholarship donors. 3. Number of scholarships awarded. 4. Number of persons applying for scholarships. 5. Amounts of scholarships in bachelor's, master's and doctoral studies (EUR). 6. Volume of scholarships (EUR). | Increasing scholarships, donations and partnerships | 2022 | Sven Illing | Elinor Toming
| 27 | Alumni and today’s students are our greatest asset and we welcome them back to the university to develop themselves, share experiences and cooperate. | 1. Number of alumni with whom the university has contact and who are active after completing their studies. 2. Number of alumni involved in the advisory boards of study programmes. 3. Number of regular fixed-format alumni events. 4. Number of alumni participating in alumni events. | Involvement of alumni in partnerships and realization of the university's development goals | 2022 | Sven Illing | Elena Kirt
| 28 | We act as a bridge between different research fields and academic generations and we are able to use the contribution of our alumni for the benefit of the university.
Organisation and management
Organisation and management Organisation and management | 29 | Tallinn University of Technology is distinguished by its climate smartness and energy efficiency and it is a smart city test centre. | 1. Sustainable and Climate Neutral University 2035 (concept, action plan and indicators). | The concept of a sustainable and climate-neutral university | 2022 | Tiit Land | Helen Sooväli-Sepping
| 30 | The university practices inclusive, value-based management and management decisions are adopted with an aim of fostering high-level studies and research. | 1. The projects of the implementation plan are available in SMART. 2. Success rate of the implementation plan and development projects. 3. The key indicators of the Strategic Plan are available. 4. The indicators of the implementation plan are available. 5. Managers have up-to-date data for decision making as a result of OOP. | Harmonizing reporting and ensuring real-time traceability | 2023 | Tiit Land | Martin Malm
| 31 | The university provides seamless, efficient and cost-effective support services with an aim to support and better integrate high-quality studies, research and innovation. | 1. Satisfaction index of the services provided. 2. Ratio between persons satisfied and persons dissatisfied. | Administrative process analysis | 2022 | Tiit Land | Martin Malm
| 32 | Our support services shall be user-oriented and developed using the once-only principle. | 1. Satisfaction index of the services provided. 2. Ratio between persons satisfied and persons dissatisfied. 3. Implementation of OOP in financial management (integrated information systems - AD, NAV, Delta, BI,…). | ALPHA project | 2025 | Tiit Land | Kaja Kuivjõgi
| 33 | The university practices inclusive, value-based management and management decisions are adopted with an aim of fostering high-level studies and research. | 1. The figures and reports concerning the Strategic Plan, implementation plan and university are available in BI; 2. High quality raw data (collected in the course of processes, the definitions of which have been agreed) | Development of the data warehouse and monitoring reports | 2022 | Tiit Land | Marden Nõmm
| 34 | The university practices inclusive, value-based management and management decisions are adopted with an aim of fostering high-level studies and research. | 1. Regulations are clear, understandable, unambiguous and easy to find for executors / responsible persons. 2. Satisfaction index of the services provided. | Reviewing and streamlining of general legislation | 2022 | Tiit Land | Laur Hiob
| 35 | The university practices inclusive, value-based management and management decisions are adopted with an aim of fostering high-level studies and research. | 2. Amendments to the Statutes based on the analysis. | Analysis of the organization management model | 2022 | Tiit Land | Martin Malm
| 36 | The university practices inclusive, value-based management and management decisions are adopted with an aim of fostering high-level studies and research. | 1. Level defined on a 4-level scale and number of proposed amendments. 2. Number of regulations and administrative systems and percentage of their compliance with standards / legislation and the need for university services. 3. Number of approved data protection impact assessments and information security risk analyses and percentage of compliance with the need for university services. 4. Number of data protection and information security consultations and trainings, evaluation of feedback and increase of the level of awareness. | Development of data processing principles and policies | 2023 | Tiit Land | Henri Schasmin
| 37 | The university's environments, both physical and virtual, are convenient and sustainable. | 1. A strategy for sustainable and targeted infrastructure management. 2. Efficiency/occupancy rate/cost-effectiveness of the usage of space. 3. Up-to-dateness of spaces. 4. Square meters per employee/per student. | Development of core infrastructure strategies | 2024 | Tiit Land | Kaja Kuivjõgi, Marden Nõmm
| 38 | To this end, together with partners from the EuroTech Universities Alliance, we lay a foundation for the Europe's most influential centre of engineering and economics education. | 1. Qualitative level of cooperation partners (based on rankings). 2. Number of structural units and/or areas involved in strategic cooperation. 3. Number of cooperation projects with strategic partners (EuroTech/EuroTeQ). 4. Number and share of ECTS credit points transferred from study abroad. | Agreeing strategic directions and principles of internationalization | 2022 | Tiit Land | Reijo Karu
| 39 | Tallinn University of Technology is visible in Estonia and internationally. | 1. Position in different rankings: focusing on Times Higher Education, THE. | Improving the position in international rankings | 2025 | Tiit Land | Reijo Karu
| 40 | They attract talented employees and facilitate interaction with our former members of the university family, prospective students and entrepreneurs. | 1. Number of spectators in games, average in a competition. 2. Number of staff engaged in sports (number of annual membership cards). 3. Number of participants in main events. 4. Number of fan club members. 5. Number of students who have registered for the course Basics of Physical Movement. 6. Sports club Share of Voice. 7. Sponsorship income (private funding). 8. Results / medals. 9. Strategic partnerships. 10. Infrastructure development. 11. Sales revenue from external customers | Implementation of the sports club development plan | 2025 | Hendrik Voll | Rait Käbin
| 41 | We improve our career system so as to better support capable, entrepreneurial and effective members of the academic staff, who contribute to research, studies and serving society. | 1. Share of academic staff attested with a positive grade in the total number of attested staff. 2. Correspondence of the level of attested academic staff to the levels set out in the academic evaluation matrix - index to be created. 3. Percentage of associate and assistant professors of all the professors. | Renewed academic career organization | 2021 | Tiit Land | Tea Trahov, Maarja Kruusmaa, Hendrik Voll
| 42 | Tallinn University of Technology is visible in Estonia and internationally. | 1. The indicator is under development. | Development of employer brand development principles | 2022 | Tea Trahov | Tea Trahov, Anne Muldme
| 43 | Our university family is tight-knit and family-friendly and fosters employees’ personal fulfilment and we value diversity as the cornerstone of academic freedom and the driving force of breakthrough research and innovation. | 1. Inverse of the Duncan Segregation Index | Gender integration analysis | 2023 | Tea Trahov | Tea Trahov
| 44 | Our university family is tight-knit and family-friendly and fosters employees’ personal fulfilment and we value diversity as the cornerstone of academic freedom and the driving force of breakthrough research and innovation. | 1. TRIM index characterising employee engagement | Increasing employee commitment | on regular basis | Tea Trahov | Tea Trahov
| 45 | The university provides seamless, efficient and cost-effective support services with an aim to support and better integrate high-quality studies, research and innovation. | 1. Quality indicator - satisfaction with IT management 2. Quality indicator - satisfaction with IT infrastructure 3. Quality indicator - satisfaction with the multimedia service 4. Efficiency indicator - 90% of the public auditoriums are supplied presentation technology complying with the standard. 5. Quality indicator - employees’ satisfaction with their computer workplace 6. Quality indicator - university members’ satisfaction with their study workplace 7. Quality indicator - level of availability of systems 8. Quality indicator - number of incidents (incl. crises) 9. Quality indicator - satisfaction with information systems 10. Quality indicator - satisfaction with the IT Helpdesk service 11. Efficiency indicator - IT procurement standard: delivery of orders to the customer within three working days from the submission of the order (if in stock). | Preparation of a long-term IT action plan | 2021 | Tea Trahov | Raul Hanson
| 46 | The university provides seamless, efficient and cost-effective support services with an aim to support and better integrate high-quality studies, research and innovation. |  | Upgrading and modernizing IT infrastructures | 1. 2022 2. 2023 3. 2022 | Tea Trahov | Edgars Žigurs
| 47 | The university provides seamless, efficient and cost-effective support services with an aim to support and better integrate high-quality studies, research and innovation. |  | Implementation of the IT development process and user experience sharing (ALPHA sync ) | 1. 2021 2. 2025 | Tea Trahov | Simar Tuula
| 48 | Tallinn University of Technology is visible in Estonia and internationally. | 1. Reputation index - TRIM in the general sample (incl. by target group) 2. Visibility index - Share of Voice (SOV) based on Station data 3. Increase of organic traffic on Google 4. Increase of keyword searches on Google 5. Reputation surveys of international rankings | Increasing reputation and visibility in Estonia and internationally | 2025 | Tea Trahov | Epp Joala,Anne Muldme, Hele-Riin Pihel, Reijo Karu
| 49 | Tallinn University of Technology is visible in Estonia and internationally. |  | Creating a TalTech Media Lab | Autumn 2022 | Tea Trahov | Anne Muldme
| 50 | Support services are developed in cooperation with the academic staff, mutually acknowledging each other's contribution and understanding each other's expectations. | 1. Number of services with described and agreed standards and their share in all support services 2. Share of services made available in the total number of services 3. Share of services to which feedback is provided in the total number of services 4. Share of SLA based services in the total number of services | Establishing support passports and service level standards | 2021 methodology, framework and pilots (IT, real estate, staff. 2022 50% of the services 2023 90% of the services | Tea Trahov | Brita Laurfeld
| 51 | Our support services shall be user-oriented and developed using the once-only principle. | 1. Index measuring customers’ satisfaction with the service/service groups. 2.Ratio of customers satisfied and customers dissatisfied with the services/service groups. | Improving the availability and satisfaction with support services | 2023 | Tea Trahov | Brita Laurfeld
| 52 | The university forms a whole regardless of the location | 1. Carbon footprint. 2. The amount of real estate actively used by the university. 3. Cost-effectiveness of the use of real estate in active use of the university. 4. Rental income from registered immovable and real estate owned by the university. | The concept of real estate management and development | 1. stage I - 2021, stage II - 2022 May. 2. Analysis of space utilization (see STRB). 3. The concept of real estate management and development (2022 May incl. analysis and proposals for finding additional sources of income from real estate | Aivar Uutar | Aivar Uutar
The university's environments, both physical and virtual, are convenient and sustainable.
| 53 | The university practices inclusive, value-based management and management decisions are adopted with an aim of fostering high-level studies and research. | 1. Amount and changes in consolidated operating income. 2. Balance of operating income and operating expenses (the result of economic activity shall be cumulatively positive in the period 2021-2025). 3. Amount of and changes in investments. 4. Accounting is performed in electronic environments, the single-entry principle has been applied and smart data visualisation tools are used. 5. Satisfaction of internal customers with the services provided by the Finance Office. 6. Satisfaction of the employees of the Finance Office, i.e. the service providers. | Development and implementation of new financial regulations | 1. 2021 development 2. 2022 implementation | Tiit Land | Tauno Tuisk
| 54 | The university practices inclusive, value-based management and management decisions are adopted with an aim of fostering high-level studies and research. |  | Implementation of activity-based costing and revenue accounting principles | Activity - based costing and revenue accounting principles agreed - 2021 Implementation of activity-based costing and revenue accounting principles - 01.01.2022. | Tauno Tuisk | Margit Pado
| 55 | Support services are developed in cooperation with the academic staff, mutually acknowledging each other's contribution and understanding each other's expectations. |  | User-centered financial management services | 1. Module for generating project reports 2021 2. Budgeting module 2021 3. ALPHA project activities 2025 | Tauno Tuisk | 1. Siret Malleus 2. Margit Pado 3. Tauno Tuisk