## Table of Contents
Table “TalTech Risk Matrix” Important links where you can read more about risk management. Risk management - https://portal.taltech.ee/wiki/show/et:uldjuhtimine:riskijuhtimine:main SMART (risk management) - https://smart.taltech.ee/protsess/riskide-juhtimine/ Definitions of key terms in the table: “Owner” means a person or unit responsible for mitigating the risk. “Person/unit responsible” means a person or unit (or several units) responsible for the implementation of the listed risk mitigation measure.
No | RISK TYPE (I - strategic, university-wide II - sectoral risk) | NUMBER OF RISK | DOMAIN | GROUP | RISK FORMULATION | RISK OWNER | STRUCTURAL UNIT RESPONSIBLE FOR THE RISK | SCORE | REFERENCE TO THE STRATEGIC PLAN
1 | I | Risk 1 | Management | B | Long-term, consistent underestimation of management quality and management risks in the management of competitive funding agreements/projects puts the university’s competitiveness and reputation as a whole at high risk. | Rector | Strategy Office | 12 | Sentence 27: The university practices inclusive, value-based management and management decisions are adopted with an aim of fostering high-level studies and research.
2 | I | Risk 2 | Management | C | Lack of transparency of the university’s internal funding models and fund rules devalues the quality of confidence management. | Rector | Strategy Office | 4 | Sentence 11: To this end, we further develop the university's internal funding model, which would mitigate the risks of ambitious and entrepreneurial research groups and promote cooperation between research groups in the university's strategic research areas.
3 | I | Risk 3 | Management/Policy | B | Inadequate readiness of the university to prevent or mitigate risks resulting from changes in state policies, laws and funding measures puts the financial continuity and competitiveness of the university at risk. | Rector | Strategy Office | 12 | Sentence 12: We will increase the university's competitive research funding and assist research groups in applying for funding, in particular in the university's strategic research areas.
4 | II | Risk 4 | Management/Policy | C | Insufficient awareness and failure to see security, external relations related and political risks in selecting cooperation partners can cause reputational damage. | Head of International Cooperation | Head of International Cooperation | 9 | Sentence 17: We enhance our international reputation through cooperation with top universities and research-intensive companies in the world. To this end, together with partners from the EuroTech Universities Alliance, we lay a foundation for the Europe's most influential centre of engineering and economics education.
5 | I | Risk 5 | Research | B | The financial uncertainty and underfunding of the tenure system undermines the sustainability and attractiveness of an academic career in the long run. | Vice-Rector for Research | Research Administration Office | 9 | Sentence 13: We improve our career system so as to better support capable, entrepreneurial and effective members of the academic staff, who contribute to research, studies and serving society.
6 | I | Risk 6 | Research | C | Lack of proactive internal coordination in initiating horizontal cooperation may lead to failure to obtain financing from key funding measures. | Vice-Rector for Research | Research Administration Office | 6 | Sentence 11: To this end, we further develop the university's internal funding model, which would mitigate the risks of ambitious and entrepreneurial research groups and promote cooperation between research groups in the university's strategic research areas.
7 | I | Risk 7 | Research | B | The interruption of the funding of research groups puts the sustainability of research groups and research directions at risk. | Vice-Rector for Research | Research Administration Office | 6 | Sentence 10: We support sustainable, responsible and high-level research groups that make a significant contribution to teaching and serving society. Sentence 11: To this end, we further develop the university's internal funding model, which would mitigate the risks of ambitious and entrepreneurial research groups and promote cooperation between research groups in the university's strategic research areas.
8 | I | Risk 8 | Research | C | Unmanaged education and research infrastructure lifespan can hinder competitive teaching and learning and research activities. | Vice-Rector for Research | Research Administration Office | 6 | Sentence 36: The university's environments, both physical and virtual, are convenient and sustainable. They shall attract talented employees and facilitate interaction with our former members of the university family, prospective students and entrepreneurs.
9 | II | Risk 9 | Research | A | Violation (disregarding) of academic integrity and good scientific practice in research. | Head of the Research Administration Office | Research Administration Office | 4 | Sentence 8: At TalTech, high-level research is conducted, which serves as the basis for applications, studies and research-intensive innovation. Our research results are published in high-level scientific publications and the doctoral theses defended at the university are predominantly based on such research. Sentence 29: High academic culture and evidence-based approach to problem solving help to turn disagreements into a breeding ground for new ideas and a practical mind helps to quickly implement the solutions.
10 | I | Risk 10 | Research staff/salary | B | Failing to build an adequate next Estonian-speaking academic generation puts the sustainability of Estonian-language higher education and the competitiveness of research at risk. | Vice-Rector for Research (shall involve Vice-Rector for Academic Affairs) | Research Administration Office (shall involve the Office of Academic Affairs) | 9 | Sentence 24: We stand for the preservation of the Estonian language and culture, primarily by providing higher education in Estonian, launching domestic spin-off and start-up companies and developing Estonian as research language.
11 | II | Risk 11 | Research | A | Damage to the reputation and credibility of the university due to violation of good practices of teaching and research ethics in I and II level of studies. | Study Director | Office of Academic Affairs | 6 | Sentence 1: Our graduates are able to solve real-life problems with their evidence-based mindset, practical engineering skills, good self-management and cooperation skills and entrepreneurial spirit. They are ready to take responsibility for the development of the Estonian economy and are in high demand in the international labour market.
12 | I | Risk 12 | Research staff/salary | B | The low competitiveness of an academic career (relatively low wages of teaching staff/PhD students/researchers on the labour market) makes it difficult to recruit and retain staff and attract a new generation of teaching staff. | Vice-Rector for Academic Affairs (shall involve Vice-Rector for Research) | Office of Academic Affairs (shall involve the Research Administration Office) | 20 | Sentence 13: We improve our career system so as to better support capable, entrepreneurial and effective members of the academic staff, who contribute to research, studies and serving society.
13 | II | Risk 13 | Research staff/salary | C | Limited opportunities to recruit and keep top professionals in the field at the university, affects the competitiveness of the university in the long term. | Director for Administration | Human Resources Office | 6 | Sentence 13: We improve our career system so as to better support capable, entrepreneurial and effective members of the academic staff, who contribute to research, studies and serving society.
14 | II | Risk 14 | Research staff/salary | C | Lack of clarity regarding resignation of underperforming tenured professors damages the reputation of the academic career and the dignity of professors. | Director for Administration | Human Resources Office | 4 | Sentence 13: We improve our career system so as to better support capable, entrepreneurial and effective members of the academic staff, who contribute to research, studies and serving society.
15 | II | Risk 15 | Management/Data | C | Lack of a uniform data policy and inadequate data management diminishes the credibility and competitiveness of the university as a strategic or leading partner. | Data Protection Officer (shall involve the head of the IT Services Office and the head of the HPC Centre) | Data Protection Officer (shall involve the head of the IT Services Office and the head of the HPC Centre, etc.) | 8 | Sentence 33: The university provides seamless, efficient and cost-effective support services with an aim to support and better integrate high-quality studies, research and innovation.
16 | II | Risk 16 | IT services | A | Incidents related to Moodle and the study information system can prevent teaching at critical moments. | Head of the IT Services Office (shall involve the Study Director) | IT Services (shall involve the Office of Academic Affairs) | 8 | Sentence 33: The university provides seamless, efficient and cost-effective support services with an aim to support and better integrate high-quality studies, research and innovation.
17 | II | Risk 17 | IT services | B | Inadequate preventive measures taken to prevent information security incidents related to important information assets of the university (the availability, integrity and confidentiality of data is not ensured) may cause a loss of availability of a business process, reputational damage, loss of important information. | Head of the IT Services Office (shall involve the Data Protection Officer and the head of the HPC Centre) | IT Services Office (shall involve the Data Protection Officer and the head of the HPC Centre) | 12 | Sentence 33: The university provides seamless, efficient and cost-effective support services with an aim to support and better integrate high-quality studies, research and innovation. Sentence 36: The university's environments, both physical and virtual, are convenient and sustainable. They shall attract talented employees and facilitate interaction with our former members of the university family, prospective students and entrepreneurs.
18 | II | Risk 18 | IT services | A | Some university services are unavailable or unusable due to unavailability of the computer network. | Head of IT Services Office | IT Services Office | 8 | Sentence 33: The university provides seamless, efficient and cost-effective support services with an aim to support and better integrate high-quality studies, research and innovation. Sentence 36: The university's environments, both physical and virtual, are convenient and sustainable. They shall attract talented employees and facilitate interaction with our former members of the university family, prospective students and entrepreneurs.
19 | I | Risk 19 | Crisis | C | Inadequate preparedness for crisis (e.g. a school shooting, a bomb attack or any other catastrophe) that has a direct impact on people’s lives, incl. poorly planned scenario and lack of awareness for quick response (bottom-up communication of information) and inability to quickly react in a crisis situation can put the lives of students and staff at risk. | Director for Administration | Crisis Manager | 12 | Sentence 27: The university practices inclusive, value-based management and management decisions are adopted with an aim of fostering high-level studies and research.
20 | I | Risk 20 | Crisis | A | In the event of an emergency, the university will not be able to ensure full online studies over a long period of time. | Vice-Rector for Academic Affairs | Office of Academic Affairs | 3 | Sentence 33: The university provides seamless, efficient and cost-effective support services with an aim to support and better integrate high-quality studies, research and innovation.
21 | II | Risk 21 | Finance | A | A credit risk regarding the receipt of income from students and customers | Chief Financial Officer | Finance Office | 5 | Sentence 33: The university provides seamless, efficient and cost-effective support services with an aim to support and better integrate high-quality studies, research and innovation.
22 | II | Risk 22 | Finance | A | The complexity and lack of operational efficiency of the procurement process puts at risk the timely execution of research projects, cooperation agreements and internal development projects and may affect the revenue received from projects/contracts. | Chief Financial Officer | Finance Office | 4 | Sentence 33: The university provides seamless, efficient and cost-effective support services with an aim to support and better integrate high-quality studies, research and innovation.
23 | II | Risk 23 | Finance | A | The overall risk of small-scale procurements, which, if not managed, can lead to claims for damages, violation or compliance notices issued to the university. | Chief Financial Officer | Finance Office | 3 | Sentence 33: The university provides seamless, efficient and cost-effective support services with an aim to support and better integrate high-quality studies, research and innovation.
24 | II | Risk 24 | Finance | A | Risks of recovery of targeted funding related to ineligibility of procurements. Recovery related to procurements is usually claimed when the procurements of the purchases that received targeted funding were carried out incorrectly – this applies also with retroactive effect upon implementation of new requirements. | Chief Financial Officer | Finance Office | 10 | Sentence 33: The university provides seamless, efficient and cost-effective support services with an aim to support and better integrate high-quality studies, research and innovation.
25 | I | Risk 25 | Real estate | C | Permanent underfunding of the university real estate does not allow for the sustainable development of university campuses and other real estate. | Director for Administration | Real Estate Office | 12 | Sentence 36: The university's environments, both physical and virtual, are convenient and sustainable. They shall attract talented employees and facilitate interaction with our former members of the university family, prospective students and entrepreneurs. Sentence 38: Tallinn University of Technology is distinguished by its climate smartness and energy efficiency and it is a smart city test centre. The university forms a whole regardless of the location
26 | II | Risk 26 | Real estate | A | Power outages, network connection failures, substation maintenance or emergencies damage the reliability of the IT infrastructure, research and education infrastructures and utility systems of buildings and can cause unplanned expenses. | Real Estate Development Director | Real Estate Office | 10 | Sentence 36: The university's environments, both physical and virtual, are convenient and sustainable. They shall attract talented employees and facilitate interaction with our former members of the university family, prospective students and entrepreneurs.
27 | II | Risk 27 | Working environment | C | Changes in the work environment can cause employee burnout and increase of conflict situations, which lead to disruptions in the organisation of work, deterioration of the organizational climate and work performance. | Head of Human Resources Office | Human Resources Office | 4 | Sentence 28: Our university family is tight-knit and family-friendly and fosters employees’ personal fulfilment and we value diversity as the cornerstone of academic freedom and the driving force of breakthrough research and innovation.
28 | II | Risk 28 | Working environment | A | Discrimination among the members of the university can lead to deterioration of the organizational climate, mental health disorders of individuals and great reputational damage to the university. | Head of Human Resources Office | Human Resources Office | 6 | Sentence 28: Our university family is tight-knit and family-friendly and fosters employees’ personal fulfilment and we value diversity as the cornerstone of academic freedom and the driving force of breakthrough research and innovation.
29 | II | Risk 29 | Working environment | A | Failure to comply with the occupational safety regulations leads to occupational accidents with severe consequences, which can lead to significant loss of the ability of employees to work and cause damage to the reputation of the university. | Head of Human Resources Office | Human Resources Office | 6 | Sentence 36: The university's environments, both physical and virtual, are convenient and sustainable. They shall attract talented employees and facilitate interaction with our former members of the university family, prospective students and entrepreneurs.
30 | II | Risk 30 | Management/Administration | C | Conflicts of interest in contracts may result in reputational damage or may lead to claims for damages or compliance notices issued to the university. | Chief Legal Officer | Chief Legal Officer | 4 | Sentence 29: High academic culture and evidence-based approach to problem solving help to turn disagreements into a breeding ground for new ideas and a practical mind helps to quickly implement the solutions.
31 | II | Risk 31 | Finance | A | A general decrease in purchasing power resulting from an external price shock (a sudden increase in costs makes the university suspend investments and developments or optimize more). | Chief Financial Officer | Finance Office | 9 | Sentence 11: To this end, we further develop the university's internal funding model, which would mitigate the risks of ambitious and entrepreneurial research groups and promote cooperation between research groups in the university's strategic research areas.

## Risk 1
Number of risk | Risk type | Owner | Identification of risks |  |  | Risk formulation | Risk assessment |  |  | Countermeasures | Countermeasures | Person/unit responsible | Processes | Reference to the Strategic Plan | Comment
|  |  | A risk FACTOR that triggers a risk event | Risk EVENT | IMPACT of the risk event |  | Current situation |  |  | Currently existing | Required
[7 empty] | Likelihood | Impact | Risk score
Risk 1 | I (strategic, university-wide) | Rector | 1. Non-compliance with rules and requirements, inadequate monitoring and failure to intervene proactively (intervention is reactive) lead to reclamations and recurrent audits. 2. Reactive and late intervention due to role ambiguity in the process of projects and contracts (this concerns both business projects and contracts and research projects). | 1. The university is blacklisted and ends up under continuous monitoring (e.g. under scrutiny of the EC project officers) or the progress of business cooperation projects is not smooth (quick, customer-friendly, operative) enough compared to the University of Tartu. | 1. Increasing administrative burden due to role ambiguity, reactive actions and numerous audits. 2. Negative funding decisions due to damaged reputation of the university. 3. The trust of external partners (companies, public sector, professional associations, etc.) towards the university as a cooperation partner decreases, which in turn causes a decrease in contracts and cooperation. | Long-term, consistent underestimation of management quality and management risks in the management of competitive funding agreements/projects puts the university’s competitiveness and reputation as a whole at high risk. | 4 | 3 | 12 | 1. ALPHA Project RAK 26 "ALPHA project (introducing a user-centric approach to support activities provided by the academic and administrative and support units)" | 2. Implementation of ALPHA (RAK 26) together with related projects (RAK 6, RAK 12, RAK 22, RAK 52). | Rectorate Strategy Office/Rectorate | Research and development: research projects; | Sentence 27: The university practices inclusive, value-based management and management decisions are adopted with an aim of fostering high-level studies and research.
Provision of support services for business cooperation;
[11 empty] | 3. Project management policy (one entry, OOP, user-centred approach) synchronised in the administrative and support units. | Rectorate Strategy Office (the concept of decisions)/Research Administration Office, Technology Transfer Office, Office of Academic Affairs, Finance Office, IT Services Office; | Research and development: research projects;
Provision of support services for business cooperation;
[11 empty] | 4. Clear division of roles between administrative and support and academic units throughout the life cycle of study, R&D projects and business contracts. Related projects: | Technology Transfer Office/Research Administration Office/Office of Academic Affairs + Finance Office/IT Services Office - application/implementation; | Research and development: research projects;
Provision of support services for business cooperation;
Project RAK 6 "Development of user-centric support services of R&D projects (incl. Alpha)"
Project RAK 12 "Optimization and quality improvement of business cooperation support processes (incl. ALPHA)"
Project RAK 52 “User-centered financial management services ( ALPHA sync)".
[11 empty] | 5. A shared data exchange platform and information field for managing R&D projects and business contracts and sharing information. Related projects: | Rectorate Strategy Office + Technology Transfer Office/ Research Administration Office/ Finance Office/ Information Technology Services - application/implementation; | Research and development: research projects;
[11 empty] | Project RAK 6 "Development of user-centric support services of R&D projects (incl. Alpha)" |  | Provision of support services for business cooperation;
Project RAK 12 "Optimization and quality improvement of business cooperation support processes (incl. ALPHA)"
Project RAK 22 "Implementation of the IT development process and user experience sharing (ALPHA sync )"
[11 empty] | 6. The competency model for managers and its application. | Director for Administration/Strategy Office/Academic managers | HR management

## Risk 2
Number of risk | Risk type | Owner | Identification of risks |  |  | Risk formulation | Risk assessment |  |  | Countermeasures | Countermeasures | Person/unit responsible | Processes | Reference to the Strategic Plan | Comment
|  |  | A risk FACTOR that triggers a risk event | Risk EVENT | IMPACT of the risk event |  | Current situation |  |  | Currently existing | Required
[7 empty] | Likelihood | Impact | Risk score
Risk 2 | I (strategic, university-wide) | Rector | 1. Regulations, regulatory communications management and monitoring of the implementation of regulations are insufficient. | 1. Silo mentality. 2. Distrusting the leaders, potential leadership crisis, leaders, a no-confidence motion against the management (the rector). 3. Outflow of the best staff. 4. Manipulation. | 1. A confidence crisis | Lack of transparency of the university’s internal funding models and fund rules devalues the quality of confidence management. | 2 | 2 | 4 | 1. The Financial Regulations in force. | 2. The new Financial Regulations (transparency at the university and school level). | Chief Financial Officer, Finance Office | Financial management | Sentence 11: To this end, we further develop the university's internal funding model, which would mitigate the risks of ambitious and entrepreneurial research groups and promote cooperation between research groups in the university's strategic research areas. | The new draft Financial Regulations and its explanatory memorandum have been supplemented - a dean shall prepare an explanatory memorandum of the school’s budget explaining the principles of the allocation of funds. The Finance Office shall publish the explanatory memorandums on the intranet. The Finance Office shall check the publication of information on the funding decisions.
[10 empty] | 3. The Rector’s directive regarding the creation of the funds. | 4. Making the allocations from the funds transparent on the intranet (funding decisions and reporting on the intranet). | Finance Office and fund owners; | Financial management
[11 empty] | 5. The deans shall disclose the principles of allocation of funds (in the explanatory memorandum of the school’s budget) and the allocations by department (teaching, research, business, support activities and general management) - it shall be laid down in the new Financial Regulations. | Chief Financial Officer/deans | Financial management

## Risk 3
Number of risk | Risk type | Owner | Identification of risks |  |  | Risk formulation | Risk assessment |  |  | Countermeasures | Countermeasures | Person/unit responsible | Process | Reference to the Strategic Plan | Comment
|  |  | A risk FACTOR that triggers a risk event | Risk EVENT | IMPACT of the risk event |  | Current situation |  |  | Currently existing | Required
[7 empty] | Likelihood | Impact | Risk score
Risk 3 | I (strategic, university-wide) | Rector | 1. A sudden economic downturn occurs due to a sudden economic crisis or other similar event. | 1. Baseline funding of higher education and research provided by the state decreases by 5%. | 1. Negative budget (a savings plan and using the surplus funds). | Inadequate readiness of the university to prevent or mitigate risks resulting from changes in state policies, laws and funding measures puts the financial continuity and competitiveness of the university at risk. | 3 | 4 | 12 | 1. Communication with ministry officials and politicians. | 3. Lobbying by the University Board, lobbying with the committees of the Parliament, lobbying with the ministers and the government, lobbying prior to elections. | University Board/Rector/Rectorate; | Strategic management | Sentence 12: We will increase the university's competitive research funding and assist research groups in applying for funding, in particular in the university's strategic research areas.
[10 empty] | 2. Policy development through various institutions Research and Development Council, Universities Estonia, working group of the Organisation of Research and Development Act. |  |  | Policy development
[10 empty] | 4. The Rectorate Strategy Office, the policy unit of the Research Administration Office have been established, the analytical capabilities of the university are strengthened. | 5. Agreeing on the development of strategies and policies and concrete roles at the level of the Rectorate. | Rectorate Strategy Office + related parties - Research Administration Office/Office of Academic Affairs/Technology Transfer Office/Finance Office | Strategic management
[11 empty] | 6. Development of the position of the university as an economic engine as laid down in the Strategic Plan, including development of cooperation programs and agreements with professional associations and launching of major strategic projects. | Vice-Rector for Entrepreneurship | Strategic management of entrepreneurship activities,
|  |  | 2. The agreement to invest 1% of GDP into R&D activities is not observed and/or reduction of funding of certain research activities due to changes in the rules governing the use of the EU’s Structural Funds. | 2. Funding by the Ministry of Education and Research decreases by more than 5% and/or the revenue received from R&D projects is significantly smaller (the volume of positive decisions decreases by more than 5%). | [6 empty] | 7. Continuous communication with research and development advisers and synchronisation of cooperation activities, agreeing on the leading unit. | Concept of the decision (Rectorate Strategy Office) and implementation (Technology Transfer Office/Research Administration Office) | Strategic management
|  |  | 3. Change of government, war leading to a significant change in the aliens policy (sanctions, laws, etc.). | 3. The recruitment of researchers and students from abroad decreases significantly. | 2. The loss of diversity and international dimensions leads to the so-called frog-pond effect and marginalization. |  |  |  |  | 8. RAK-project on the strategy for internationalization. RAK 32 “Agreeing on strategic directions and principles of internationalization" | 9. To review the current internationalization strategy - whether to prepare a crisis plan and activities to mitigate and prevent drastic scenarios of alien policy changes - activities targeted at students and activities targeted at researchers + e.g. to send PhD students in strategic fields to study abroad and use scholarship funds to tie them with and make them return to TalTech after their post-doctoral research in order to launch new tenures and research fields. | Head of International Cooperation/Vice-Rector for Research/Vice-Rector for Academic Affairs, etc.; | Strategic management |  | Description and preparation of various scenarios has been a topic of the discussion (e.g., the decision of the state to switch to partially or fully paid higher education, but no separate preparations are made for this, but the option is knowingly taken into account so that at the political level the positions can be proposed and calculations be presented in order to make the decision.

## Risk 4
Number of risk | Risk type | Owner | Identification of risks |  |  | Risk formulation | Risk assessment |  |  | Countermeasures | Countermeasures | Person/unit responsible | Processes | Reference to the Strategic Plan | Comment
|  |  | A risk FACTOR that triggers a risk event | Risk EVENT | IMPACT of the risk event |  | Current situation |  |  | Currently existing | Required
[7 empty] | Likelihood | Impact | Risk score
Risk 4 | II (sectoral risk) | Head of International Cooperation | 1. Cooperation is carried out with an unfavourable partner, network or programme. | 1. It turns out that the university cooperates with a nationally unfavourable partner, information on which reaches the wider public/interest groups. 2. In the course of the cooperation, the university is exploited in a way that poses a threat to security. | 1. An outcome that is damaging to reputation and/or security. | Insufficient awareness and failure to see security, external relations related and political risks in selecting cooperation partners can cause reputational damage. | 3 | 3 | 9 | 1. Various trainings and other awareness-raising activities for the members of the university. |  | Rectorate Strategy Office - Head of International Cooperation + security coordinator; | Management of international cooperation | Sentence 17: We enhance our international reputation through cooperation with top universities and research-intensive companies in the world. To this end, together with partners from the EuroTech Universities Alliance, we lay a foundation for the Europe's most influential centre of engineering and economics education.
[11 empty] | 2. Regular contacts between the representatives of various national security and policy authorities , members of the university management board and persons coordinating international cooperation. |  | Management of international cooperation

## Risk 5
Number of risk | Risk type | Owner | Identification of risks |  |  | Risk formulation | Risk assessment |  |  | Countermeasures | Countermeasures | Person/unit responsible | Processes | Reference to the Strategic Plan | Comment
|  |  | A risk FACTOR that triggers a risk event | Risk EVENT | IMPACT of the risk event |  | Current situation |  |  | Currently existing | Required
[7 empty] | Likelihood | Impact | Risk score
Risk 5 | I (strategic, university-wide) | Vice-Rector for Research | 1. Limitations and underfunding of the tenure system. | 1. Employees leave because they do not see a career perspective (especially young people, top researchers). | 1. Study programmes are closed, lack of students, decline in research productivity. | The financial uncertainty and underfunding of the tenure system undermines the sustainability and attractiveness of an academic career in the long run. | 3 | 3 | 9 | 1. The new Financial Regulations lay down clearly the financing principles of the tenure systems; the analysis of and support for deciding on tenured positions BASED ON THE CRITERIA (Power BI reports). |  | Research Administration Office | Strategic management of research; | Sentence 13: We improve our career system so as to better support capable, entrepreneurial and effective members of the academic staff, who contribute to research, studies and serving society.
|  |  | 2. A professor does not receive the funding laid down in the Financial Regulations. | [7 empty] | 2. Enforcing, incl. communication and monitoring of implementation, of the Financial Regulations. | Finance Office | Financial management
[11 empty] | 3. Increase of the funding of the general research fund at the expense of the increase in the volume of the overhead fee for projects and contracts. More projects and fewer overhead fee exemptions. | Research Administration Office/Technology Transfer Office | Research and development: research projects;
|  |  | 3. Changing decisions, constantly changing communication. | 2. It is difficult to plan the creation and filling of tenure positions | 2. A decrease in the number of filled tenure positions | [5 empty] | 4. More extensive lobbying in society to explain the importance of science and higher education (in order to increase baseline funding). | Rector/Rectorate/University Board; See also Risk 3 action 3 and action 5; | Strategic management
[11 empty] | 5. Enforcing the university's career model (tenure funding, career opportunities, quality criteria, attestation) | Research Administration Office - informing. Deans and academic managers - enforcement; | HR management

## Risk 6
Number of risk | Risk type | Owner | Identification of risks |  |  | Risk formulation | Risk assessment |  |  | Countermeasures | Countermeasures | Person/unit responsible | Processes | Reference to the Strategic Plan | Comment
|  |  | A risk FACTOR that triggers a risk event | Risk EVENT | IMPACT of the risk event |  | Current situation |  |  | Currently existing | Required
[7 empty] | Likelihood | Impact | Risk score
Risk 6 | I (strategic, university-wide) | Vice-Rector for Research | 1. Lack of or slow coordination. | 1. Development and launch of large-scale and strategic initiatives outside the university or the emergence of an in-house cross-disciplinary initiative. | 1. A financial loss that weakens the organization's capacity. | Lack of proactive internal coordination in initiating horizontal cooperation may lead to failure to obtain financing from key funding measures. | 3 | 2 | 6 | 1. Defining the strategic research areas. | 2. Determining the activities and providing support services for the strategic research areas, finding and supporting the leaders of these activities. Project RAK 4 -"Developing focus topics and linking them to university management decisions" | Research Administration Office | Strategic management of research; | Sentence 11: To this end, we further develop the university's internal funding model, which would mitigate the risks of ambitious and entrepreneurial research groups and promote cooperation between research groups in the university's strategic research areas.
[10 empty] | 3. Encouraging contacts between researchers within the university (general courses of doctoral studies, the grant accelerator, trainings, etc.). |  |  | Strategic management of research;

## Risk 7
Number of risk | Risk type | Owner | Identification of risks |  |  | Risk formulation | Risk assessment |  |  | Countermeasures | Countermeasures | Person/unit responsible | Processes | Reference to the Strategic Plan | Comment
|  |  | A risk FACTOR that triggers a risk event | Risk EVENT | IMPACT of the risk event |  | Current situation |  |  | Currently existing | Required
[7 empty] | Likelihood | Impact | Risk score
Risk 7 | I (strategic, university-wide) | Vice-Rector for Research | 1. The funding landscape changes. 2. Declining relevance of the research field. 3. Lack of competence. 4. Lack of human resources. 5. Narrow focus of the research group on single measures and donors. | 1. The research group does not receive funding. | 1. The research group terminates its operation. 2. The research direction disappears. 3. Can lead to a decline in the quality of teaching. | The interruption of the funding of research groups puts the sustainability of research groups and research directions at risk. | 3 | 2 | 6 | 1. The principles of funding tenured positions is clearly laid down in the Financial Regulations. |  | PI (principal investigator)/ the department; | Financial management | Sentence 10: We support sustainable, responsible and high-level research groups that make a significant contribution to teaching and serving society. Sentence 11: To this end, we further develop the university's internal funding model, which would mitigate the risks of ambitious and entrepreneurial research groups and promote cooperation between research groups in the university's strategic research areas. | Some researchers still expect to have the bridge funding option that provides a sense of security as in the case of the grant fund for young scientists, should the research funding of the research group terminate and the applications be unsuccessful. The discussions led to a decision that bridge funding could be guaranteed through a certain type of risk fund, the prerequisite of which is compliance of the research groups with the agreed quality and sustainability requirements (the implementation of which takes time) - the measure would be implemented in approximately 7 years.
[10 empty] | 2. Bridge funding for young scientists. |  |  | Strategic management of research;
[10 empty] | 3. Department’s reserves. Using the surplus funds for the school. |  |  | Financial management
[10 empty] | 4. Temporary execution of other projects (up to 2 years). |  |  | Strategic management of research;
[10 empty] | 5. A sufficient number of research groups allows joining other groups temporarily. |  |  | Strategic management of research;
[11 empty] | 6. Even greater support in applying for projects (diversification and planning of long-term activities of the research group) - a preventive and proactive measure. | Research Administration Office + Technology Transfer Office - helps to diversify the revenue portfolio of research groups through business cooperation; | Research and development: research projects;
[11 empty] | 7. Increasing the viability of research groups (8.5 FTE, tenure and the share of external funding) and monitoring - establishing quality requirements for research groups. |  | Strategic management of research;

## Risk 8
Number of risk | Risk type | Owner | Identification of risks |  |  | Risk formulation | Risk assessment |  |  | Countermeasures | Countermeasures | Person/unit responsible | Processes | Reference to the Strategic Plan | Comment
|  |  | A risk FACTOR that triggers a risk event | Risk EVENT | IMPACT of the risk event |  | Current situation |  |  | Currently existing | Required
[7 empty] | Likelihood | Impact | Risk score
Risk 8 | I (strategic, university-wide) | Vice-Rector for Research | 1. Infrastructure lifecycle is unmanaged. | 1. The research infrastructure is depreciated or cannot be exploited. | 1. Becoming less competitive, potential not realized | Unmanaged education and research infrastructure lifespan can hinder competitive teaching and learning and research activities. | 3 | 2 | 6 | 1. Mapping of the infrastructure, seeking funding opportunities, participation in the development of funding measures.. | 2. Project RAK 11 "Development of a sustainable (cross) use and funding model for research laboratories" | Research Administration Office | Management of the research infrastructure | Sentence 36: The university's environments, both physical and virtual, are convenient and sustainable. They shall attract talented employees and facilitate interaction with our former members of the university family, prospective students and entrepreneurs.
[11 empty] | 3. Project RAK 31 "Efficient and sustainable management of TalTech infrastructures" | Rectorate Strategy Office + input from the Research Administration Office/ Real Estate Office/Office of Academic Affairs; | Coordinating the infrastructures;
[11 empty] | 4. Development and implementation of the infrastructure cost/benefit analysis models; improving joint planning and cross-use of the infrastructure. | Research Administration Office | Management of the research infrastructure
[10 empty] | 5. The IT Services Office has mapped a dozen or so older host computers in the research infrastructure/computers (fully disconnected from the network or with restricted network connection) that need to be replaced. |  | Department | IT management;
[11 empty] | 6. Project RAK 53 "Improving the quality of e-learning and e-support" | Office of Academic Affairs; | Management of the education infrastructure
[11 empty] | 7. Project RAK 55 “Development of a digital environment supporting degree studies". | Office of Academic Affairs; | Management of the education infrastructure
[11 empty] | 8. Project RAK 54 "Improving hybrid learning capacities in classrooms". | Office of Academic Affairs; | Management of the education infrastructure

## Risk 9
Number of risk | Risk type | Owner | Identification of risks |  |  | Risk formulation | Risk assessment |  |  | Countermeasures | Countermeasures | Person/unit responsible | Processes | Reference to the Strategic Plan | Comment
|  |  | A risk FACTOR that triggers a risk event | Risk EVENT | IMPACT of the risk event |  | Current situation |  |  | Currently existing | Required
[7 empty] | Likelihood | Impact | Risk score
Risk 9 | II (sectoral risk) | Head of the Research Administration Office | 1. Possible lack of awareness of researchers, PhD students (students) of the general principles of research ethics. | 1. Violation of academic integrity and good scientific practice in research, incl. upon publication. | 1. Damage to the reputation of the university. 2. A decrease in the credibility of researchers and research, and thus a decrease in competitiveness. | Violation (disregarding) of academic integrity and good scientific practice in research. | 4 | 1 | 4 | 1. Preventive action - informing on the issues of academic integrity at the school and department level, all the members of the Academic Ethics Committee appointed from the schools disseminate information. | 2. More active dissemination of information takes place e.g. at the beginning of an academic year, in the framework of the onboarding program for new employees, from programme directors to PhD students. | Research Administration Office | Ethics; | Sentence 8: At TalTech, high-level research is conducted, which serves as the basis for applications, studies and research-intensive innovation. Our research results are published in high-level scientific publications and the doctoral theses defended at the university are predominantly based on such research. Sentence 29: High academic culture and evidence-based approach to problem solving help to turn disagreements into a breeding ground for new ideas and a practical mind helps to quickly implement the solutions.
[10 empty] | 3. Information materials on academic integrity, good practice, etc. are available on the intranet in Estonian and English. | 4. In addition, materials will be prepared by the Academic Ethics Committee and in the framework of the RAK project for informing and training different target groups. |  | Ethics;
[10 empty] | 5. The Code of Academic Ethics provides the general framework; To support and develop ethics related issues the project RAK_69 “Ethical people in an ethical university” has been launched. |  |  | Ethics;

## Risk 10
Number of risk | Risk type | Owner | Identification of risks |  |  | Risk formulation | Risk assessment |  |  | Countermeasures | Countermeasures | Person/unit responsible | Processes | Reference to the Strategic Plan | Comment
|  |  | A risk FACTOR that triggers a risk event | Risk EVENT | IMPACT of the risk event |  | Current situation |  |  | Currently existing | Required
[7 empty] | Likelihood | Impact | Risk score
Risk 10 | I (strategic, university-wide) | Vice-Rector for Research (shall involve Vice-Rector for Academic Affairs) | 1. Low funding of higher education and research, the society does not value scientific degrees. | 1. A drastic decrease in the number of Estonians in doctoral studies and at different stages of an academic career. | 1. Due to the decrease in the volume of studies in Estonian, the funding of the university decreases and the university loses its accreditation. 2. If the teaching staff are not involved in the work of a research group and the top researchers are not involved in teaching, the students may not realize the possibilities and attractiveness of a research career. | Failing to build an adequate next Estonian-speaking academic generation puts the sustainability of Estonian-language higher education and the competitiveness of research at risk. | 3 | 3 | 9 | 1. The university shall introduce more itself as an employer - make professors more visible. |  | Research Administration Office/Office of Academic Affairs/Marketing and Communications Office | HR management | Sentence 24: We stand for the preservation of the Estonian language and culture, primarily by providing higher education in Estonian, launching domestic spin-off and start-up companies and developing Estonian as research language.
[10 empty] | 2. Greater recognition of the value of teaching in the university’s career model (teaching track Associate Professors, evaluating teaching experience upon the selection and attestation of tenured professors). |  | Vice-Rector for Research/Vice-Rector for Academic Affairs | HR management
[11 empty] | 3. Increasing the baseline funding of higher education and research See also Risk 3 measure 3 | Vice-Rector for Academic Affairs and Vice-Rector for Research (state funding)/ principal investigator (attracting more competitive funding); see also Risk 12 measure 2. | Strategic management
[11 empty] | 4. Integrating the teaching staff (lecturers, senior lecturers) into research groups. | Heads of departments /principal investigator; | Strategic management of research;
[10 empty] | 5. Participation of top researchers in teaching (attestations and key performance indicators of the Strategic Plan - the share of teaching staff with a doctoral degree). |  | Vice-Rector for Academic Affairs/ Vice-Rector for Research/deans; | Strategic management of teaching
[11 empty] | 6. Introducing career paths to students, involving students in research groups. | Office of Academic Affairs/ Research Administration Office (the policy of research groups) / programme directors/principal investigator; | Degree studies
[11 empty] | 7. Additional language training for international employees. | Human Resources Office | HR management

## Risk 11
Number of risk | Risk type | Owner | Identification of risks |  |  | Risk formulation | Risk assessment |  |  | Countermeasures | Countermeasures | Person/unit responsible | Processes | Reference to the Strategic Plan | Comment
|  |  | A risk FACTOR that triggers a risk event | Risk EVENT | IMPACT of the risk event |  | Current situation |  |  | Currently existing | Required
[7 empty] | Likelihood | Impact | Risk score
Risk 11 | II (sectoral risk) | Study Director | 1. Plagiarism. | 1. Invalidating the research paper (incl. a bachelor’s or master’s thesis) and revoking the awarded academic degree. | 1. Damage to the university's reputation and loss of credibility. | Damage to the reputation and credibility of the university due to violation of good practices of teaching and research ethics in I and II level of studies. | 2 | 3 | 6 | 1. All graduation thesis and several other student papers (essays, lab reports) undergo a plagiarism check. | 2. In autumn, a document on the good practice in learning and teaching will be completed, where special emphasis will be put on the issues of ethics. | Office of Academic Affairs / supervisor | Degree studies | Sentence 1: Our graduates are able to solve real-life problems with their evidence-based mindset, practical engineering skills, good self-management and cooperation skills and entrepreneurial spirit. They are ready to take responsibility for the development of the Estonian economy and are in high demand in the international labour market.
[10 empty] | 3. The schools have prepared guidelines for writing graduation theses. The study programmes include courses that address research-related details. | 4. Continuous awareness-raising efforts and checking and condemning plagiarism. | Office of Academic Affairs/ Programme Director | Degree studies
[10 empty] | 5. The university’s legislation sets out measures for cases where there is evidence of plagiarism or other violations of good academic practice. | 6. To define the supervisor’s role and responsibilities. | Office of Academic Affairs/ Dean / Programme Director | Ethics;

## Risk 12
Number of risk | Risk type | Owner | Identification of risks |  |  | Risk formulation | Risk assessment |  |  | Countermeasures | Countermeasures | Person/unit responsible | Processes | Reference to the Strategic Plan | Comment
|  |  | A risk FACTOR that triggers a risk event | Risk EVENT | IMPACT of the risk event |  | Current situation |  |  | Currently existing | Required
[7 empty] | Likelihood | Impact | Risk score
Risk 12 | I (strategic, university-wide) | Vice-Rector for Academic Affairs (shall involve Vice-Rector for Research) | 1. Low wages of the academic staff and PhD students. | 1. Talented graduates of master’s studies take up employment outside the university. 2. In some disciplines, the teaching capability disappears since there is no new generation of teachers. 3. We have to settle for mediocre or foreign staff. | 1. The university is unable to compete in the wage market and raise its next generation of teaching staff. | The low competitiveness of an academic career (relatively low wages of teaching staff/PhD students/researchers on the labour market) makes it difficult to recruit and retain staff and attract a new generation of teaching staff. | 5 | 4 | 20 | 1. The position of Early Stage Researcher. |  | Research Administration Office/ Ddeans; | Doctoral studies | Sentence 13: We improve our career system so as to better support capable, entrepreneurial and effective members of the academic staff, who contribute to research, studies and serving society.
[10 empty] | 2. No wage ceiling. If the unit can provide funding, the amount of the wages can be set at the level of the wage market. See also Risk 13 measure 1 |  | Human Resources Office | HR management
[11 empty] | 3. Increase in state funding (KPI of the Strategic Plan). Lobbying in the Ministry of Education and Research. | Office of Academic Affairs; | Strategic management
[11 empty] | 4. New Financial Regulations that help raise awareness of the importance of teaching. | Office of Academic Affairs / Finance Office | Strategic management of teaching
[11 empty] | 5. To increase the wages of the teaching staff (different categories) using the additional funds received by the university. | Dean/Heads of Departments (implementation); | Strategic management of teaching
[11 empty] | 6. Strong research groups that can pay additional remuneration to academic staff (including teaching staff and in order to attract talented PhD students). | Research Administration Office; See also the viability of research groups - Risk 7. | Strategic management of research;

## Risk 13
Number of risk | Risk type | Owner | Identification of risks |  |  | Risk formulation | Risk assessment |  |  | Countermeasures | Countermeasures | Person/unit responsible | Processes | Reference to the Strategic Plan | Comment
|  |  | A risk FACTOR that triggers a risk event | Risk EVENT | IMPACT of the risk event |  | Current situation |  |  | Currently existing | Required
[7 empty] | Likelihood | Impact | Risk score
Risk 13 | II (sectoral risk) | Director for Administration | 1. Recruitment process 2 . Career management 3. Remuneration policy 4. Geopolitical position 5. Aggression 6. Economic crisis 7. Adjustment problems | 1. 10% leave the university. | 1. The development of the disciplines would be hampered. | Limited opportunities to recruit and keep top professionals in the field at the university, affects the competitiveness of the university in the long term. | 2 | 3 | 6 | 1. No wage ceiling. If the unit can provide funding, the amount of the wages can be set at the level of the wage market. |  | Human Resources Office | HR management | Sentence 13: We improve our career system so as to better support capable, entrepreneurial and effective members of the academic staff, who contribute to research, studies and serving society. | The staff have high degree of discretion in their academic activities to develop their field of activity.
[10 empty] | 2. The reputation of the university is good and improving, the working environment of the university is appealing. | 3. Creation and launch of the university's employer brand. Consciously increasing the prominence and visibility of the top performers. | Human Resources Office / Marketing and Communications Office; | Marketing and communication;
HR management
[10 empty] | 4. The organization of work at the university makes it possible to maintain a good work-life balance if desired. |  | Human Resources Office/ immediate superiors | HR management
[10 empty] | 5. The development of central support services is aimed at reducing the administrative problems of employees and simplifying solutions. (RAK projects) | 6. Project RAK 51 "Improving the availability and satisfaction with support services” | Human Resources Office/ Support Service Development Manager | Quality monitoring
[11 empty] | 7. Projec tRAK 50 "Establishing support passports and service level standards". |  | Quality management;
[11 empty] | 8. To make the leadership program available and update it. The development of leadership skills helps to increase the ability of units to support the improvement of the working environment and remuneration of top performers. | Human Resources Office/ Academic managers | HR management
[11 empty] | 9. Development and implementation of employee onboarding programs. | Human Resources Office/ Academic managers | HR management
[11 empty] | 10. Development and implementation of employee offboarding programs (incl. development of the culture of exit interviews). | Human Resources Office/ Academic managers | HR management

## Risk 14
Number of risk | Risk type | Owner | Identification of risks |  |  | Risk formulation | Risk assessment |  |  | Countermeasures | Countermeasures | Person/unit responsible | Processes | Reference to the Strategic Plan | Comment
|  |  | A risk FACTOR that triggers a risk event | Risk EVENT | IMPACT of the risk event |  | Current situation |  |  | Currently existing | Required
[7 empty] | Likelihood | Impact | Risk score
Risk 14 | II (sectoral risk) | Director for Administration | 1. Underperformance. Successful tenured employees do not encounter this. | 1. A person who has failed an attestation and has not reached retirement age yet. | 1. The person is upset. 2. The issue can escalate outside the university. | Lack of clarity regarding resignation of underperforming tenured professors damages the reputation of the academic career and the dignity of professors. | 4 | 1 | 4 | 1. Appointment to Professor Emeritus/Emerita status is a valued opportunity for transitioning of well-performing professors to retirement. |  | Human Resources Office | HR management | Sentence 13: We improve our career system so as to better support capable, entrepreneurial and effective members of the academic staff, who contribute to research, studies and serving society.
[10 empty] | 2. Attestation and annual interviews also ensure that tenured professors are constantly aware of the evaluation of their work performance and help to avoid the unpleasantness of sudden resignation resulting from underperformance. |  | Immediate superior/ head of the research group/director/dean | HR management
[10 empty] | 3. Providing support to managers in solving personal, complex cases - staff and communication |  | Human Resources Office/immediate superior (incl. appraisal interviews)/deans/directors | HR management
[11 empty] | 4. Development of leadership skills, regular feedback on work performance | Immediate superior/ head of the research group/director/dean | HR management

## Risk 15
Number of risk | Risk type | Owner | Identification of risks |  |  | Risk formulation | Risk assessment |  |  | Countermeasures | Countermeasures | Person/unit responsible | Processes | Reference to the Strategic Plan | Comment
|  |  | A risk FACTOR that triggers a risk event | Risk EVENT | IMPACT of the risk event |  | Current situation |  |  | Currently existing | Required
[7 empty] | Likelihood | Impact | Risk score
Risk 15 | II (sectoral risk) | Data Protection Officer (shall involve the head of the IT Services Office and the head of the HPC Centre) | 1. Violation of applicable regulations (due to ignorance) - e.g.: DataManagementPlan in projects or violation of the provisions of GDPR. | 1. A violation is detected by the partner, in the course of an audit or inspection. | 1. The project donor requests recovery. 2. Cooperation/a contract is terminated, no opportunity to compete in the following rounds - financial and reputational damage. | Lack of a uniform data policy and inadequate data management diminishes the credibility and competitiveness of the university as a strategic or leading partner. | 2 | 4 | 8 | 1. Carrying out regular audits and daily monitoring of data processing and protection. | 2. Carrying out additional inspections of data processing and protection. | Data Protection Officer | Data protection and information security management; | Sentence 33: The university provides seamless, efficient and cost-effective support services with an aim to support and better integrate high-quality studies, research and innovation.
[10 empty] | 3. Regularly updating /supplementing data processing, protection and information security regulations and management systems. | 4. Updating the data processing and protection management system. Supplementing and implementing the data processing and protection policy project. |  | Data protection and information security management;
[10 empty] | 5. Assessment of data processing and protection and information security risks. | 6. Supplementing the data processing and protection and information security risk assessment (the university’s new higher level risk assessment). |  | Data protection and information security management;
[10 empty] | 7. Daily counselling and regular training of university members on data protection and information security. | 8. Supplementing trainings on data protection and information security (the university’s new face-to-face and online trainings). |  | Data protection and information security management;
[11 empty] | 9. Project RAK 30 "Development of data processing principles and policies". |  | Data protection and information security management;

## Risk 16
Number of risk | Risk type | Owner | Identification of risks |  |  | Risk formulation | Risk assessment |  |  | Countermeasures | Countermeasures | Person/unit responsible | Processes | Reference to the Strategic Plan | Comment
|  |  | A risk FACTOR that triggers a risk event | Risk EVENT | IMPACT of the risk event |  | Current situation |  |  | Currently existing | Required
[7 empty] | Likelihood | Impact | Risk score
Risk 16 | II (sectoral risk) | Head of the IT Services Office (shall involve the Study Director) | 1. Cyber attack. 2. Incorrect configuration. 3. A hardware error. 4. A software error. 5. A network error. | 1. An incident (unplanned disruption or error) in Moodle and/or in the study information system. | 1. Studies are disrupted, the impact is especially critical during the exam period. | Incidents related to Moodle and the study information system can prevent teaching at critical moments. | 4 | 2 | 8 | 1. A service-level agreement regarding Moodle to ensure that work can be performed according to requirements. | 2. An SLA for the maintenance of the study information system application shall be agreed with the Office of Academic Affairs. | IT Services Office together with the Office of Academic Affairs | IT management; | Sentence 33: The university provides seamless, efficient and cost-effective support services with an aim to support and better integrate high-quality studies, research and innovation.
[10 empty] | 3. We monitor solutions in order to react as quickly as possible or proactively. |  |  | IT management;
[10 empty] | 4. We have talented IT specialists. |  |  | HR management
[10 empty] | 5. We have concluded agreements with the development partners whom we can involve in case of incidents. |  |  | IT management;
[10 empty] | 6. We have set a chain for incident response. |  |  | IT management;
[10 empty] | 7. We develop software and make configurations in compliance with the best practice in the field of IT. | 8. Preparation and practising of recovery plans. |  | IT development
[10 empty] | 9. The data in the information systems are backed up. | 10. Preparation and practising of recovery plans. |  | IT management;

## Risk 17
Number of risk | Risk type | Owner | Identification of risks |  |  | Risk formulation | Risk assessment |  |  | Countermeasures | Countermeasures | Person/unit responsible | Processes | Reference to the Strategic Plan | Comment
|  |  | A risk FACTOR that triggers a risk event | Risk EVENT | IMPACT of the risk event |  | Current situation |  |  | Currently existing | Required
[7 empty] | Likelihood | Impact | Risk score
Risk 17 | II (sectoral risk) | Head of the IT Services Office (shall involve the Data Protection Officer and the head of the HPC Centre) | 1. Unawareness of the users regarding information security risks (information assets are handled carelessly or not in compliance with the established measures. 2. Cyber attacks. 3. Configuration errors. 4. Inadequate security measures. | 1. An information security incident (the availability, integrity and confidentiality of data is not ensured). | 1. A loss of availability of a business process, reputational damage, loss of important information. | Inadequate preventive measures taken to prevent information security incidents related to important information assets of the university (the availability, integrity and confidentiality of data is not ensured) may cause a loss of availability of a business process, reputational damage, loss of important information. | 4 | 3 | 12 | 1. We develop software and make configurations in compliance with the best practice in the field of IT. |  | Information Technology Services Office | Data protection and information security management; | Sentence 33: The university provides seamless, efficient and cost-effective support services with an aim to support and better integrate high-quality studies, research and innovation. Sentence 36: The university's environments, both physical and virtual, are convenient and sustainable. They shall attract talented employees and facilitate interaction with our former members of the university family, prospective students and entrepreneurs.
[10 empty] | 2. We monitor solutions in order to react as quickly as possible or proactively. |  |  | Data protection and information security management;
[10 empty] | 3. We apply reasonable security measures. |  |  | Data protection and information security management;
[10 empty] | 4. The information security policy has been prepared and implemented. | 5. Implementation of the Estonian Information Security Standard. |  | Data protection and information security management;
[10 empty] | 6. We develop software and make configurations in compliance with the best practice in the field of IT. |  |  | IT development
[10 empty] | 7. Information assets have been backed up. |  |  | IT management;
[11 empty] | 8. Raising the awareness of the members of the university about data handling and information security. |  | Data protection and information security management;

## Risk 18
Number of risk | Risk type | Owner | Identification of risks |  |  | Risk formulation | Risk assessment |  |  | Countermeasures | Countermeasures | Person/unit responsible | Processes | Reference to the Strategic Plan | Comment
|  |  | A risk FACTOR that triggers a risk event | Risk EVENT | IMPACT of the risk event |  | Current situation |  |  | Currently existing | Required
[7 empty] | Likelihood | Impact | Risk score
Risk 18 | II (sectoral risk) | Head of IT Services Office | 1. Failure of network devices, including outdated devices. 2. Cyber attack. 3. Configuration errors. | 1. The computer network is not available. | 1. Disruption of the availability of various processes and services dependent on the computer network. | Some university services are unavailable or unusable due to unavailability of the computer network. | 4 | 2 | 8 | 1. Regular updating of network equipments. | 2. To regularly update network equipment and ensure permanent funding for that. | IT Services Office | IT management; | Sentence 33: The university provides seamless, efficient and cost-effective support services with an aim to support and better integrate high-quality studies, research and innovation. Sentence 36: The university's environments, both physical and virtual, are convenient and sustainable. They shall attract talented employees and facilitate interaction with our former members of the university family, prospective students and entrepreneurs.
[10 empty] | 3. Using backup UPSs for networking equipment. |  |  | IT management;
[10 empty] | 4. The architecture and configuration of the network equipment shall be such that the failure of one device does not result in a loss of availability of the entire network. |  |  | IT management;
[10 empty] | 5. Network monitoring and incident response capability. |  |  | IT management;

## Risk 19
Number of risk | Risk type | Owner | Identification of risks |  |  | Risk formulation | Risk assessment |  |  | Countermeasures | Countermeasures | Person/unit responsible | Processes | Reference to the Strategic Plan | Comment
|  |  | A risk FACTOR that triggers a risk event | Risk EVENT | IMPACT of the risk event |  | Current situation |  |  | Currently existing | Required
[7 empty] | Likelihood | Impact | Risk score
Risk 19 | I (strategic, university-wide) | Director for Administration | 1. An event causing crisis (e.g. shooting). | 1. Incorrect response due to poorly prepared crisis management/response. The countermeasures are inadequate. | 1. The crisis escalates more than it could have. 2. We solve it worse than we could have. For example, we are unable to localize a dangerous individual (lock the person in a room). | Inadequate preparedness for crisis (e.g. a school shooting, a bomb attack or any other catastrophe) that has a direct impact on people’s lives, incl. poorly planned scenario and lack of awareness for quick response (bottom-up communication of information) and inability to quickly react in a crisis situation can put the lives of students and staff at risk. | 4 | 3 | 12 | 1. Regular activities preparing for crisis management and response have been carried out, but there are areas that have not been covered (e.g. technological crisis). | 2. Planning and implementation of additional activities required for the university’s preparedness for crisis management and response. Updating of various crisis management plans and schemes. | Crisis manager; | Crisis management | Sentence 27: The university practices inclusive, value-based management and management decisions are adopted with an aim of fostering high-level studies and research. | Crisis management process.
[10 empty] | 3. The university’s crisis management procedures, teams, roles and plans have been prepared and established, but they need to be updated and supplemented. | 4. The university’s crisis management and response regulations need to be updated and supplemented in terms of organisational changes and additional crisis situations (e.g. war situation, technological crisis), in order to have action plans for possible different crisis situations. The crisis manager has been designated and team roles have been updated. |  | Crisis management
[10 empty] | 5. The awareness of the members of the university has been raised through corrsponding communication. | 6. Raising the awareness of the members of the university (regarding the principles of crisis resolution) by strengthening the corresponding communication. |  | Crisis management
[10 empty] | 7. Crisis management and resolution trainings and exercises in key areas have been provided at the university annually, but the trainings and exercises need to be organized regularly and systematically. | 8. Regular and systematic planning and conduct of university’s crisis management and resolution trainings and exercises in key areas. |  | Crisis management
[10 empty] | 9. The university has functioning technical solutions and other tools for crisis management and resolution, but there are some uncovered areas. | 10. Ensuring the systemic functioning of crisis management and resolution by complementing the university’s technical solutions and other tools for crisis management and resolution. |  | Crisis management
[11 empty] | 11. Additional locking systems (doors that can be locked from the inside) for sheltering from sudden attacks. | Real Estate Office | Security services and protection of property

## Risk 20
Number of risk | Risk type | Owner | Identification of risks |  |  | Risk formulation | Risk assessment |  |  | Countermeasures | Countermeasures | Person/unit responsible | Processes | Reference to the Strategic Plan | Comment
|  |  | A risk FACTOR that triggers a risk event | Risk EVENT | IMPACT of the risk event |  | Current situation |  |  | Currently existing | Required
[7 empty] | Likelihood | Impact | Risk score
Risk 20 | I (strategic, university-wide) | Vice-Rector for Academic Affairs | 1. An epidemic, war, fire, an extreme weather phenomenon (flood, storm). | 1. It is impossible to use the university’s teaching infrastructure (destroyed, a lockdown, an epidemic, etc.). | 1. Teaching (face-to-face teaching) cannot be carried out in the premises of the university. | In the event of an emergency, the university will not be able to ensure full online studies over a long period of time. | 1 | 3 | 3 | 1. E-support is provided for most of the courses in Moodle; licences with the possibility to access virtual learning environments. |  | Office of Academic Affairs; | Degree studies | Sentence 33: The university provides seamless, efficient and cost-effective support services with an aim to support and better integrate high-quality studies, research and innovation.
[10 empty] | 2. Guidelines and information materials have been prepared for e-learning and Proctorio licenses have been purchased for online examinations. |  |  | Degree studies
[10 empty] | 3. The teaching staff have long-term (3 semesters) online teaching experience. |  |  | Degree studies
[11 empty] | 4. The possibilities for carrying out laboratory work and practical training virtually or at home. |  | Degree studies

## Risk 21
Number of risk | Risk type | Owner | Identification of risks |  |  | Risk formulation | Risk assessment |  |  | Countermeasures | Countermeasures | Person/unit responsible | Processes | Reference to the Strategic Plan | Comment
|  |  | A risk FACTOR that triggers a risk event | Risk EVENT | IMPACT of the risk event |  | Current situation |  |  | Currently existing | Required
[7 empty] | Likelihood | Impact | Risk score
Risk 21 | II (sectoral risk) | Chief Financial Officer | 1. Students don't have enough money. | 1. Students fail to pay the tuition fees on time. | 1. Low financial impact. | A credit risk regarding the receipt of income from students and customers | 5 | 1 | 5 | 1. The process of handling outstanding receivables (reminders + debt collection). | 2. To draw up a process guide, to describe the best practices (Finance Ofice) - what can be checked by the persons responsible. | Finance Office | Degree studies | Sentence 33: The university provides seamless, efficient and cost-effective support services with an aim to support and better integrate high-quality studies, research and innovation. | The process has not been described formally, but works in practice. Three reminders are sent in case of student debts, cooperation with the departments, the possibility to reschedule debts. Thereafter the debt is transferred to a collection agency. Annual credit loss is rather optimized (EUR 15 thousand per year).
[11 empty] | 3. Documenting, notifying of and providing training regarding the debt handling process. | Dean’s offices /Finance Office | Degree studies
|  |  | 2. Companies don't pay bills. | 2. Companies don’t pay bills on time. | [5 empty] | 4. The process of handling outstanding bills (reminders + debt collection). | 5. To draw up a process guide, to describe the best practices (Finance Ofice) - what can be checked by the persons responsible. | Finance Office | Provision of support services for business cooperation; |  | The process has not been described formally, but works in practice. Three reminders are sent in case of debts, cooperation with the departments, thereafter the debt is transferred to a collection agency. The development of sales reporting is already underway (in June 2022), it provides an overview more rapidly when payment defaults occur. There is an effectively functioning system where the debts are relatively quicly transferred to a collection agency and credit losses are minimized effectively (EUR 30 thousand/year).
[11 empty] | 6. Sales reports (submitted + current overview of outstanding bills). | Technology Transfer Office / Finance Office | Provision of support services for business cooperation;

## Risk 22
Number of risk | Risk type | Owner | Identification of risks |  |  | Risk formulation | Risk assessment |  |  | Countermeasures | Countermeasures | Person/unit responsible | Processes | Reference to the Strategic Plan | Comment
|  |  | A risk FACTOR that triggers a risk event | Risk EVENT | IMPACT of the risk event |  | Current situation |  |  | Currently existing | Required
[7 empty] | Likelihood | Impact | Risk score
Risk 22 | II (sectoral risk) | Chief Financial Officer | 1. Too many procurements at a time or procurement planning is started too late. | 1. Procurement contracts between the contracting parties are not concluded by the required deadlines. | 1. The execution of projects or business contracts is delayed, there are no valid framework contracts for the necessary services, which in turn can lead to a recourse claim. | The complexity and lack of operational efficiency of the procurement process puts at risk the timely execution of research projects, cooperation agreements and internal development projects and may affect the revenue received from projects/contracts. | 4 | 1 | 4 | 1. An integrated procurement process. | 2. An environment for small purchases. | Finance Office | Organisation of procurements | Sentence 33: The university provides seamless, efficient and cost-effective support services with an aim to support and better integrate high-quality studies, research and innovation. | Procurements have become more complex over time (more services, fewer products) and volumes have increased, more disputes have been filed and supervision has become more stringent, but the human resources are limited. A constant problem is that the contracting authority starts with the procurement process too late and lack of quality and experience of the contracting authorities in setting requirements. The environment for small purchases is under development in 2022, it will enable reopening of a competition under framework agreements in a more convenient and easily auditable way in the future. Trainings have been organized irregularly.
[10 empty] | 3. Preparation of a procurement plan (twice a year). | 4. Additional procurement specialists and or legal officers are required. |  | Organisation of procurements
[11 empty] | 5. Reviewing of the procurement process, further optimisation, design of procurement documentation and performance analysis of procurement processes. |  | Organisation of procurements
[11 empty] | 6. Regular trainings for contracting authorities about the procurement process. |  | Organisation of procurements

## Risk 23
Number of risk | Risk type | Owner | Identification of risks |  |  | Risk formulation | Risk assessment |  |  | Countermeasures | Countermeasures | Person/unit responsible | Processes | Reference to the Strategic Plan | Comment
|  |  | A risk FACTOR that triggers a risk event | Risk EVENT | IMPACT of the risk event |  | Current situation |  |  | Currently existing | Required
[7 empty] | Likelihood | Impact | Risk score
Risk 23 | II (sectoral risk) | Chief Financial Officer | 1. Structural units buy products and services on their own in small quantities without a procurement process, so that the total limits that would require the organization of proper procurements are exceeded. | 1. During the audit, it is discovered that the total limit has been exceeded and the public procurement obligation has been violated. | 1. If the purchase was made under a target-financed project, it can lead to recourse claims, in other cases just a reprimand, warning, observation, etc. | The overall risk of small-scale procurements, which, if not managed, can lead to claims for damages, violation or compliance notices issued to the university. | 3 | 1 | 3 | 1. The procurement assistants manually check compliance with the limits. | 2. An environment for small purchases. | Finance Office | Organisation of procurements | Sentence 33: The university provides seamless, efficient and cost-effective support services with an aim to support and better integrate high-quality studies, research and innovation. | In the environment for small purchases it should be possible to categorize purchases so that the thresholds for the purchases can be monitored. (The categories are subjective and not clearly defined)

## Risk 24
Number of risk | Risk type | Owner | Identification of risks |  |  | Risk formulation | Risk assessment |  |  | Countermeasures | Countermeasures | Person/unit responsible | Processes | Reference to the Strategic Plan | Comment
|  |  | A risk FACTOR that triggers a risk event | Risk EVENT | IMPACT of the risk event |  | Current situation |  |  | Currently existing | Required
[7 empty] | Likelihood | Impact | Risk score
Risk 24 | II (sectoral risk) | Chief Financial Officer | 1. Either the framework agreement and the purchases made under it during the project or the procurement made directly for the purchase of the project is rejected. | 1. A funder files a recovery claim, because it is considered that the purchases made under the project do not comply with the requirements. | 1. Financial damage from recovery claims. | Risks of recovery of targeted funding related to ineligibility of procurements. Recovery related to procurements is usually claimed when the procurements of the purchases that received targeted funding were carried out incorrectly – this applies also with retroactive effect upon implementation of new requirements. | 5 | 2 | 10 | 1. The procurement procedure and an integrated procurement process. | 2. An environment for small purchases. | Finance Office | Organisation of procurements | Sentence 33: The university provides seamless, efficient and cost-effective support services with an aim to support and better integrate high-quality studies, research and innovation. | Procurements have become more complex over time (more services, fewer products) and volumes have increased, more disputes have been filed and supervision has become more stringent, but the human resources are limited. A constant problem is that the contracting authority starts with the procurement process too late and lack of quality and experience of the contracting authorities in setting requirements. The environment for small purchases is under development in 2022, it will enable reopening of a competition under framework agreements in a more convenient and easily auditable way in the future. Trainings have been organized irregularly.
[11 empty] | 3. Additional procurement specialists and or legal officers are required. |  | Organisation of procurements
[11 empty] | 4. Reviewing of the procurement process, further optimisation, design of procurement documentation and performance analysis of procurement processes. |  | Organisation of procurements
[11 empty] | 5. Regular trainings for contracting authorities about the procurement process. |  | Organisation of procurements

## Risk 25
Number of risk | Risk type | Owner | Identification of risks |  |  | Risk formulation | Risk assessment |  |  | Countermeasures | Countermeasures | Person responsible | Processes | Reference to the Strategic Plan | Comment
|  |  | A risk FACTOR that triggers a risk event | Risk EVENT | IMPACT of the risk event |  | Current situation |  |  | Currently existing | Required
[7 empty] | Likelihood | Impact | Risk score
Risk 25 | I (strategic, university-wide) | Director for Administration | 1. Underfunding that does not cover real estate depreciation and emergency building repairs. | 1. A building is unusable, the state authorities request closure of the building. | 1. Teaching and research are disrupted. 2. Damage to reputation. | Permanent underfunding of the university real estate does not allow for the sustainable development of university campuses and other real estate. | 4 | 3 | 12 | 1. The new version of the Financial Regulations, which will enter into force in July of 2022, lay down that real estate shall be financed as the first priority and allows the real estate fund to be allocated before the budget is distributed between the units. | 2. Continuous and adequate funding must be agreed upon and allocated annually. | Director for Administration /Finance Office | Financial management | Sentence 36: The university's environments, both physical and virtual, are convenient and sustainable. They shall attract talented employees and facilitate interaction with our former members of the university family, prospective students and entrepreneurs. Sentence 38: Tallinn University of Technology is distinguished by its climate smartness and energy efficiency and it is a smart city test centre. The university forms a whole regardless of the location
[10 empty] | 3. The annual rental income and capital budget allocated to the Real Estate Office is inadequate. | 4. Preparation of the university's real estate development plan, which creates a basis for increasing real estate profitability. | Director for Administration/ Real Estate Office | Real estate and campus management

## Risk 26
Number of risk | Risk type | Owner | Identification of risks |  |  | Risk formulation | Risk assessment |  |  | Countermeasures | Countermeasures | Person/unit responsible | Processes | Reference to the Strategic Plan | Comment
|  |  | A risk FACTOR that triggers a risk event | Risk EVENT | IMPACT of the risk event |  | Current situation |  |  | Currently existing | Required
[7 empty] | Likelihood | Impact | Risk score
Risk 26 | II (sectoral risk) | Real Estate Development Director | 1. Long- and short-term external power outages and voltage fluctuations. 2. Failure of the systems and equipment controlling the power supply of the university’s real estate (e.g. air conditioning systems stop working) | 1. Devices stop working, become inoperative or start working in the wrong mode when turned on. 2. Air conditioner system failures. | 1. Devices stop working - repairs can be very expensive and take a long time. 2. Research processes are disrupted causing great losses in terms of research and materials. 3. IT equipment overheats and the operation of applications or the network is disrupted. 4. If the insurance does not cover the replacement/repair of the equipment, it is an unplanned expense. | Power outages, network connection failures, substation maintenance or emergencies damage the reliability of the IT infrastructure, research and education infrastructures and utility systems of buildings and can cause unplanned expenses. | 5 | 2 | 10 | 1. The server rooms are partially (in the SOC and ITC buildings) supplied with UPS systems and generators. | 2. High-risk real estate related equipment, systems and rooms must be mapped by building and the need for additional equipment must be determined. | Real Estate Office | Real estate and campus management | Sentence 36: The university's environments, both physical and virtual, are convenient and sustainable. They shall attract talented employees and facilitate interaction with our former members of the university family, prospective students and entrepreneurs.
[11 empty] | 3. Generation capacity must be increased and UPSs should be employed for each piece of critical equipment. If necessary, back-up duplication in critical locations. |  | Real estate and campus management
[10 empty] | 4. Equipment insurance (the contract will expire). | 5. The needs to insure the equipment of the academic units must be mapped, a new procurement must be conducted and the academic units shall be informed of the insurance guarantee. |  | Real estate and campus management
[10 empty] | 6. Regular inspection and assessment of the condition of equipment and utility networks owned by the university. | 7. Supplementing the financial scheme for replacing outdated or broken equipment (cooling equipment, heating equipment). |  | Maintenance of buildings and facilities;
[10 empty] | 8. The procedure for responding to and solving incidents defined in contracts to manage the quality of the service provided by the partners. | 9. Regular review of contracts. |  | Maintenance of buildings and facilities;
[11 empty] | 10. It is necessary to define the criteria, when the impact of a risk increases and the risk turns into crisis and a crisis situation must be declared. |  | Crisis management |  | See also Risk 19 “Preparedness for crisis”
[10 empty] | 11. Autonomous power supply of security and access control systems for 12-24 hours. | 12. High-risk rooms must be mapped. Mitigation actions must be planned based on it. |  | Security services and protection of property

## Risk 27
Number of risk | Risk type | Owner | Identification of risks |  |  | Risk formulation | Risk assessment |  |  | Countermeasures | Countermeasures | Person/unit responsible | Processes | Reference to the Strategic Plan | Comment
|  |  | A risk FACTOR that triggers a risk event | Risk EVENT | IMPACT of the risk event |  | Current situation |  |  | Currently existing | Required
[7 empty] | Likelihood | Impact | Risk score
Risk 27 | II (sectoral risk) | Head of Human Resources Office | 1. The COVID-19 emergency, resulting in workers being forced to work remotely. | 1. A change in the work procedure causes employees’ depression and stress and the incidence of illness increases. | 1. Work may be disrupted in all areas of the university’s activities, work efficiency drops, employee motivation decreases. | Changes in the work environment can cause employee burnout and increase of conflict situations, which lead to disruptions in the organisation of work, deterioration of the organizational climate and work performance. | 4 | 1 | 4 | 1. The services of psychologists working at the university under a contract are available to all the employees. |  | Human Resources Office/ heads of units | HR management | Sentence 28: Our university family is tight-knit and family-friendly and fosters employees’ personal fulfilment and we value diversity as the cornerstone of academic freedom and the driving force of breakthrough research and innovation.
[10 empty] | 2. A specific occupational physician consulting service providing mental health support to employees. |  |  | HR management
[10 empty] | 3. An employee can choose a suitable form of work by agreement with his/her superior. | 4. Training of managers. |  | HR management
[10 empty] | 5. The HR Office and Office of Academic Affairs provide assistance to managers in solving conflict situations. |  |  | HR management
[10 empty] | 6. The procedure for processing appeals and complaints is laid down in the Conciliation Procedure and a procedure has been laid down for whistleblowing. |  |  | HR management
[11 empty] | 7. Intentional communication on the topic and training of problem recognition skills. |  | HR management

## Risk 28
Number of risk | Risk type | Owner | Identification of risks |  |  | Risk formulation | Risk assessment |  |  | Countermeasures | Countermeasures | Person/unit responsible | Processes | Reference to the Strategic Plan | Comment
|  |  | A risk FACTOR that triggers a risk event | Risk EVENT | IMPACT of the risk event |  | Current situation |  |  | Currently existing | Required
[7 empty] | Likelihood | Impact | Risk score
Risk 28 | II (sectoral risk) | Head of Human Resources Office | 1. Lack of awareness, increased stress levels or difference between value judgements of the members of the university. | 1. Discriminatory behaviour that causes the discriminated party’s need for protection. | 1. Reputational damage if the case gets media attention. 2. Decrease in employee satisfaction with the university. 3. Potential lawsuits. | Discrimination among the members of the university can lead to deterioration of the organizational climate, mental health disorders of individuals and great reputational damage to the university. | 3 | 2 | 6 | 1. Defining and disclosing the principles, drawing up an action plan. | 2. Raising situational awareness through data disclosure and training. | Human Resources Office | HR management | Sentence 28: Our university family is tight-knit and family-friendly and fosters employees’ personal fulfilment and we value diversity as the cornerstone of academic freedom and the driving force of breakthrough research and innovation.
[10 empty] | 3. The Conciliation Procedure, which lays down the procedure for the resolution of cases of discrimination at the university. | 4. Promoting the best practices through seminars and briefings. |  | HR management
[10 empty] | 5. Setting the goal of gender balance for the university as one of the key indicators in the Strategic Plan. |  |  | HR management

## Risk 29
Number of risk | Risk type | Owner | Identification of risks |  |  | Risk formulation | Risk assessment |  |  | Countermeasures | Countermeasures | Person/unit responsible | Processes | Reference to the Strategic Plan | Comment
|  |  | A risk FACTOR that triggers a risk event | Risk EVENT | IMPACT of the risk event |  | Current situation |  |  | Currently existing | Required
[7 empty] | Likelihood | Impact | Risk score
Risk 29 | II (sectoral risk) | Head of Human Resources Office | 1. Accidents happen to employees due to a lack of knowledge about occupational safety or an unsafe working environment. | 1. Occupational accident | 1. Decrease in the employee’s ability to work. 2. Lower level of employee satisfaction with the activities of the university. 3. Precepts or fines issued by supervisory bodies. 4. Damage to the university’s reputation if the incident is covered by the news media. | Failure to comply with the occupational safety regulations leads to occupational accidents with severe consequences, which can lead to significant loss of the ability of employees to work and cause damage to the reputation of the university. | 3 | 2 | 6 | 1. Existence and up-to-dateness of regulations, risk assessments and safety instructions. | 2. A digital environment for managing and using documents. | Chief Work Environment Specialist; | HR management | Sentence 36: The university's environments, both physical and virtual, are convenient and sustainable. They shall attract talented employees and facilitate interaction with our former members of the university family, prospective students and entrepreneurs.
[10 empty] | 3. Supervision and training. | 4. Digital training opportunities, reporting on completion of compulsory training. |  | HR management
[11 empty] | 5. Substantive organisation and quality of the work of working environment representatives. |  | HR management

## Risk 30
Number of risk | Risk type | Owner | Identification of risks |  |  | Risk formulation | Risk assessment |  |  | Countermeasures | Countermeasures | Person/unit responsible | Processes | Reference to the Strategic Plan | Comment
|  |  | A risk FACTOR that triggers a risk event | Risk EVENT | IMPACT of the risk event |  | Current situation |  |  | Currently existing | Required
[7 empty] | Likelihood | Impact | Risk score
Risk 30 | II (sectoral risk) | Chief Legal Officer | 1. An employee has inadequate ethical standards. 2. An employee has lack of knowledge of conflict of interest (e.g. also the aspects of corruption). 3. The control mechanisms for preventing and managing conflicts of interest are inadequate. | 1. The university purchases a service/product at a price higher than the market price or purchases an unsuitable service/product of inferior quality, or enters into a contract without checking the aspects regarding corruption (e.g. an employee purchases from his/her own undertaking, etc.). | 1. Financial loss, as well as use of inappropriate equipment because there is no money to buy a suitable device/equipment or financial or reputational damage caused by corruption. | Conflicts of interest in contracts may result in reputational damage or may lead to claims for damages or compliance notices issued to the university. | 4 | 1 | 4 | 1. The Procedure for Avoiding a Conflict of Interests and Preventing Corruption. |  | Chief Legal Officer | The support process for legal services; | Sentence 29: High academic culture and evidence-based approach to problem solving help to turn disagreements into a breeding ground for new ideas and a practical mind helps to quickly implement the solutions.
[10 empty] | 2. The course ““Preventing corruption and conflicts of interest in the public sector” available in Moodle. | 3. Additional trainings, continuous informing, to supplement ”Examples of possible conflicts of interest and a code of conduct”. |  | The support process for legal services;
[11 empty] | 4. To review the contracting process and potential risks. |  | Internal Audit Office

## Risk 31
Number of risk | Risk type | Owner | Identification of risks |  |  | Risk formulation | Risk assessment |  |  | Countermeasures | Countermeasures | Person responsible | Processes | Reference to the Strategic Plan | Comment
|  |  | A risk FACTOR that triggers a risk event | Risk EVENT | IMPACT of the risk event |  | Current situation |  |  | Currently existing | Required
[7 empty] | Likelihood | Impact | Risk score
Risk 31 | II (sectoral risk) | Chief Financial Officer | 1. Combined impact of macroeconomic and political factors. | 1. Exponential increase of external costs and wages in the labour market within a short period of time. | 1. The university’s real purchasing power decreases, significant cuts must be made, volumes must be reduced. | A general decrease in purchasing power resulting from an external price shock (a sudden increase in costs makes the university suspend investments and developments or optimize more). | 3 | 3 | 9 | 1. Decentralized financial management (Financial Regulations) ensure that each unit shall achieve a budget balance and save costs, if necessary. | 2. Centrally, at the level of units and the University Board, opportunities for optimisation and cost savings and optimisation are sought through university-wide agreements (real estate, use of space, economy, etc.). | Chief Financial Officer/ Finance Office/Academic managers | Financial management | Sentence 11: To this end, we further develop the university's internal funding model, which would mitigate the risks of ambitious and entrepreneurial research groups and promote cooperation between research groups in the university's strategic research areas. | From 10.2022, the cost of real estate use has been based on actual external costs for the final consumer, fixed previously.
[11 empty] | 3. Analysis of the options to fix external prices. | Chief Financial Officer/ Finance Office | Financial management |  | In the case of services, the price of which is increasing, opportunities are sought to reduce consumption (in 2022 energy). The pricing of the services sold must cover own expenditure (cost increase is passed on to customers), but most of the university’s revenue does not allow flexible passing-on of a cost increase. Structural units can use historical reserves (surplus) to temporarily withstand losses if the situation is not permanent or can be compensated by revenue growth in the future. The structural units can also seek temporary solutions by using internal loans.

## Summary
No | NUMBER OF RISK | RISK TYPE | RISK OWNER | RISK FORMULATION | RISK ASSESSMENT - Likelihood | RISK ASSESSMENT - Impact | RISK ASSESSMENT - Risk score | COUNTERMEASURES (Currently existing) | COUNTERMEASURES (Required) | PERSONS/UNITS RESPONSIBLE for the measures | Risk-related PROCESS(ES)
1 | Risk 1 | I (strategic, university-wide) | Rector | Long-term, consistent underestimation of management quality and management risks in the management of competitive funding agreements/projects puts the university’s competitiveness and reputation as a whole at high risk. | 4 | 3 | 12 | 1. ALPHA Project RAK 26 "ALPHA project (introducing a user-centric approach to support activities provided by the academic and administrative and support units)" | 2. Implementation of ALPHA (RAK 26) together with related projects (RAK 6, RAK 12, RAK 22, RAK 52). 3. Project management policy (one entry, OOP, user-centred approach) synchronised in the administrative and support units. 4. Clear division of roles between administrative and support and academic units throughout the life cycle of study, R&D projects and business contracts. Related projects: Project RAK 6 "Development of user-centric support services of R&D projects (incl. Alpha)" Project RAK 12 "Optimization and quality improvement of business cooperation support processes (incl. ALPHA)" Project RAK 52 “User-centered financial management services ( ALPHA sync)". 5. A shared data exchange platform and information field for managing R&D projects and business contracts and sharing information. Related projects: Project RAK 6 "Development of user-centric support services of R&D projects (incl. Alpha)" Project RAK 12 "Optimization and quality improvement of business cooperation support processes (incl. ALPHA)" Project RAK 22 "Implementation of the IT development process and user experience sharing (ALPHA sync )" 6. The competency model for managers and its application. | Rectorate Strategy Office/Rectorate Rectorate Strategy Office (the concept of decisions)/Research Administration Office, Technology Transfer Office, Office of Academic Affairs, Finance Office, IT Services Office; Technology Transfer Office/Research Administration Office/Office of Academic Affairs + Finance Office/IT Services Office - application/implementation; Rectorate Strategy Office + Technology Transfer Office/ Research Administration Office/ Finance Office/ Information Technology Services - application/implementation; Director for Administration/Strategy Office/Academic managers | Research and development: research projects; Provision of support services for business cooperation; Research and development: research projects; Provision of support services for business cooperation; Research and development: research projects; Provision of support services for business cooperation; Research and development: research projects; Provision of support services for business cooperation; HR management
2 | Risk 2 | I (strategic, university-wide) | Rector | Lack of transparency of the university’s internal funding models and fund rules devalues the quality of confidence management. | 2 | 2 | 4 | 1. The Financial Regulations in force. 3. The Rector’s directive regarding the creation of the funds. | 2. The new Financial Regulations (transparency at the university and school level). 4. Making the allocations from the funds transparent on the intranet (funding decisions and reporting on the intranet). 5. The deans shall disclose the principles of allocation of funds (in the explanatory memorandum of the school’s budget) and the allocations by department (teaching, research, business, support activities and general management) - it shall be laid down in the new Financial Regulations. | Chief Financial Officer, Finance Office Finance Office and fund owners; Chief Financial Officer/deans | Financial management Financial management Financial management
3 | Risk 3 | I (strategic, university-wide) | Rector | Inadequate readiness of the university to prevent or mitigate risks resulting from changes in state policies, laws and funding measures puts the financial continuity and competitiveness of the university at risk. | 3 | 4 | 12 | 1. Communication with ministry officials and politicians. 2. Policy development through various institutions Research and Development Council, Universities Estonia, working group of the Organisation of Research and Development Act. 4. The Rectorate Strategy Office, the policy unit of the Research Administration Office have been established, the analytical capabilities of the university are strengthened. 8. RAK-project on the strategy for internationalization. RAK 32 “Agreeing on strategic directions and principles of internationalization" | 3. Lobbying by the University Board, lobbying with the committees of the Parliament, lobbying with the ministers and the government, lobbying prior to elections. 5. Agreeing on the development of strategies and policies and concrete roles at the level of the Rectorate. 6. Development of the position of the university as an economic engine as laid down in the Strategic Plan, including development of cooperation programs and agreements with professional associations and launching of major strategic projects. 7. Continuous communication with research and development advisers and synchronisation of cooperation activities, agreeing on the leading unit. 9. To review the current internationalization strategy - whether to prepare a crisis plan and activities to mitigate and prevent drastic scenarios of alien policy changes - activities targeted at students and activities targeted at researchers + e.g. to send PhD students in strategic fields to study abroad and use scholarship funds to tie them with and make them return to TalTech after their post-doctoral research in order to launch new tenures and research fields. | University Board/Rector/Rectorate; Rectorate Strategy Office + related parties - Research Administration Office/Office of Academic Affairs/Technology Transfer Office/Finance Office Vice-Rector for Entrepreneurship Concept of the decision (Rectorate Strategy Office) and implementation (Technology Transfer Office/Research Administration Office) Head of International Cooperation/Vice-Rector for Research/Vice-Rector for Academic Affairs, etc.; | Strategic management Policy development Strategic management Strategic management of entrepreneurship activities, Strategic management Strategic management
4 | Risk 4 | II (sectoral risk) | Head of International Cooperation | Insufficient awareness and failure to see security, external relations related and political risks in selecting cooperation partners can cause reputational damage. | 3 | 3 | 9 | 1. Various trainings and other awareness-raising activities for the members of the university. | 2. Regular contacts between the representatives of various national security and policy authorities , members of the university management board and persons coordinating international cooperation. | Rectorate Strategy Office - Head of International Cooperation + security coordinator; | Management of international cooperation Management of international cooperation
5 | Risk 5 | I (strategic, university-wide) | Vice-Rector for Research | The financial uncertainty and underfunding of the tenure system undermines the sustainability and attractiveness of an academic career in the long run. | 3 | 3 | 9 | 1. The new Financial Regulations lay down clearly the financing principles of the tenure systems; the analysis of and support for deciding on tenured positions BASED ON THE CRITERIA (Power BI reports). | 2. Enforcing, incl. communication and monitoring of implementation, of the Financial Regulations. 3. Increase of the funding of the general research fund at the expense of the increase in the volume of the overhead fee for projects and contracts. More projects and fewer overhead fee exemptions. 4. More extensive lobbying in society to explain the importance of science and higher education (in order to increase baseline funding). 5. Enforcing the university's career model (tenure funding, career opportunities, quality criteria, attestation) | Research Administration Office Finance Office Research Administration Office/Technology Transfer Office Rector/Rectorate/University Board; See also Risk 3 action 3 and action 5; Research Administration Office - informing. Deans and academic managers - enforcement; | Strategic management of research; Financial management Research and development: research projects; Strategic management HR management
6 | Risk 6 | I (strategic, university-wide) | Vice-Rector for Research | Lack of proactive internal coordination in initiating horizontal cooperation may lead to failure to obtain financing from key funding measures. | 3 | 2 | 6 | 1. Defining the strategic research areas. 3. Encouraging contacts between researchers within the university (general courses of doctoral studies, the grant accelerator, trainings, etc.). | 2. Determining the activities and providing support services for the strategic research areas, finding and supporting the leaders of these activities. Project RAK 4 -"Developing focus topics and linking them to university management decisions" | Research Administration Office | Strategic management of research; Strategic management of research;
7 | Risk 7 | I (strategic, university-wide) | Vice-Rector for Research | The interruption of the funding of research groups puts the sustainability of research groups and research directions at risk. | 3 | 2 | 6 | 1. The principles of funding tenured positions is clearly laid down in the Financial Regulations. 2. Bridge funding for young scientists. 3. Department’s reserves. Using the surplus funds for the school. 4. Temporary execution of other projects (up to 2 years). 5. A sufficient number of research groups allows joining other groups temporarily. | 6. Even greater support in applying for projects (diversification and planning of long-term activities of the research group) - a preventive and proactive measure. 7. Increasing the viability of research groups (8.5 FTE, tenure and the share of external funding) and monitoring - establishing quality requirements for research groups. | PI (principal investigator)/ the department; Research Administration Office + Technology Transfer Office - helps to diversify the revenue portfolio of research groups through business cooperation; | Financial management Strategic management of research; Financial management Strategic management of research; Strategic management of research; Research and development: research projects; Strategic management of research;
8 | Risk 8 | I (strategic, university-wide) | Vice-Rector for Research | Unmanaged education and research infrastructure lifespan can hinder competitive teaching and learning and research activities. | 3 | 2 | 6 | 1. Mapping of the infrastructure, seeking funding opportunities, participation in the development of funding measures.. 5. The IT Services Office has mapped a dozen or so older host computers in the research infrastructure/computers (fully disconnected from the network or with restricted network connection) that need to be replaced. | 2. Project RAK 11 "Development of a sustainable (cross) use and funding model for research laboratories" 3. Project RAK 31 "Efficient and sustainable management of TalTech infrastructures" 4. Development and implementation of the infrastructure cost/benefit analysis models; improving joint planning and cross-use of the infrastructure. 6. Project RAK 53 "Improving the quality of e-learning and e-support" 7. Project RAK 55 “Development of a digital environment supporting degree studies". 8. Project RAK 54 "Improving hybrid learning capacities in classrooms". | Research Administration Office Rectorate Strategy Office + input from the Research Administration Office/ Real Estate Office/Office of Academic Affairs; Research Administration Office Department Office of Academic Affairs; Office of Academic Affairs; Office of Academic Affairs; | Management of the research infrastructure Coordinating the infrastructures; Management of the research infrastructure IT management; Management of the education infrastructure Management of the education infrastructure Management of the education infrastructure
9 | Risk 9 | II (sectoral risk) | Head of the Research Administration Office | Violation (disregarding) of academic integrity and good scientific practice in research. | 4 | 1 | 4 | 1. Preventive action - informing on the issues of academic integrity at the school and department level, all the members of the Academic Ethics Committee appointed from the schools disseminate information. 3. Information materials on academic integrity, good practice, etc. are available on the intranet in Estonian and English. 5. The Code of Academic Ethics provides the general framework; To support and develop ethics related issues the project RAK_69 “Ethical people in an ethical university” has been launched. | 2. More active dissemination of information takes place e.g. at the beginning of an academic year, in the framework of the onboarding program for new employees, from programme directors to PhD students. 4. In addition, materials will be prepared by the Academic Ethics Committee and in the framework of the RAK project for informing and training different target groups. | Research Administration Office | Ethics; Ethics; Ethics;
10 | Risk 10 | I (strategic, university-wide) | Vice-Rector for Research (shall involve Vice-Rector for Academic Affairs) | Failing to build an adequate next Estonian-speaking academic generation puts the sustainability of Estonian-language higher education and the competitiveness of research at risk. | 3 | 3 | 9 | 1. The university shall introduce more itself as an employer - make professors more visible. 2. Greater recognition of the value of teaching in the university’s career model (teaching track Associate Professors, evaluating teaching experience upon the selection and attestation of tenured professors). 5. Participation of top researchers in teaching (attestations and key performance indicators of the Strategic Plan - the share of teaching staff with a doctoral degree). | 3. Increasing the baseline funding of higher education and research See also Risk 3 measure 3 4. Integrating the teaching staff (lecturers, senior lecturers) into research groups. 6. Introducing career paths to students, involving students in research groups. 7. Additional language training for international employees. | Research Administration Office/Office of Academic Affairs/Marketing and Communications Office Vice-Rector for Research/Vice-Rector for Academic Affairs Vice-Rector for Academic Affairs and Vice-Rector for Research (state funding)/ principal investigator (attracting more competitive funding); see also Risk 12 measure 2. Heads of departments /principal investigator; Vice-Rector for Academic Affairs/ Vice-Rector for Research/deans; Office of Academic Affairs/ Research Administration Office (the policy of research groups) / programme directors/principal investigator; Human Resources Office | HR management HR management Strategic management Strategic management of research; Strategic management of teaching Degree studies HR management
11 | Risk 11 | II (sectoral risk) | Study Director | Damage to the reputation and credibility of the university due to violation of good practices of teaching and research ethics in I and II level of studies. | 2 | 3 | 6 | 1. All graduation thesis and several other student papers (essays, lab reports) undergo a plagiarism check. 3. The schools have prepared guidelines for writing graduation theses. The study programmes include courses that address research-related details. 5. The university’s legislation sets out measures for cases where there is evidence of plagiarism or other violations of good academic practice. | 2. In autumn, a document on the good practice in learning and teaching will be completed, where special emphasis will be put on the issues of ethics. 4. Continuous awareness-raising efforts and checking and condemning plagiarism. 6. To define the supervisor’s role and responsibilities. | Office of Academic Affairs / supervisor Office of Academic Affairs/ Programme Director Office of Academic Affairs/ Dean / Programme Director | Degree studies Degree studies Ethics;
12 | Risk 12 | I (strategic, university-wide) | Vice-Rector for Academic Affairs (shall involve Vice-Rector for Research) | The low competitiveness of an academic career (relatively low wages of teaching staff/PhD students/researchers on the labour market) makes it difficult to recruit and retain staff and attract a new generation of teaching staff. | 5 | 4 | 20 | 1. The position of Early Stage Researcher. 2. No wage ceiling. If the unit can provide funding, the amount of the wages can be set at the level of the wage market. See also Risk 13 measure 1 | 3. Increase in state funding (KPI of the Strategic Plan). Lobbying in the Ministry of Education and Research. 4. New Financial Regulations that help raise awareness of the importance of teaching. 5. To increase the wages of the teaching staff (different categories) using the additional funds received by the university. 6. Strong research groups that can pay additional remuneration to academic staff (including teaching staff and in order to attract talented PhD students). | Research Administration Office/ Ddeans; Human Resources Office Office of Academic Affairs; Office of Academic Affairs / Finance Office Dean/Heads of Departments (implementation); Research Administration Office; See also the viability of research groups - Risk 7. | Doctoral studies HR management Strategic management Strategic management of teaching Strategic management of teaching Strategic management of research;
13 | Risk 13 | II (sectoral risk) | Director for Administration | Limited opportunities to recruit and keep top professionals in the field at the university, affects the competitiveness of the university in the long term. | 2 | 3 | 6 | 1. No wage ceiling. If the unit can provide funding, the amount of the wages can be set at the level of the wage market. 2. The reputation of the university is good and improving, the working environment of the university is appealing. 4. The organization of work at the university makes it possible to maintain a good work-life balance if desired. 5. The development of central support services is aimed at reducing the administrative problems of employees and simplifying solutions. (RAK projects) | 3. Creation and launch of the university's employer brand. Consciously increasing the prominence and visibility of the top performers. 6. Project RAK 51 "Improving the availability and satisfaction with support services” 7. Projec tRAK 50 "Establishing support passports and service level standards". 8. To make the leadership program available and update it. The development of leadership skills helps to increase the ability of units to support the improvement of the working environment and remuneration of top performers. 9. Development and implementation of employee onboarding programs. 10. Development and implementation of employee offboarding programs (incl. development of the culture of exit interviews). | Human Resources Office Human Resources Office / Marketing and Communications Office; Human Resources Office/ immediate superiors Human Resources Office/ Support Service Development Manager Human Resources Office/ Academic managers Human Resources Office/ Academic managers Human Resources Office/ Academic managers | HR management Marketing and communication; HR management HR management Quality monitoring Quality management; HR management HR management HR management
14 | Risk 14 | II (sectoral risk) | Director for Administration | Lack of clarity regarding resignation of underperforming tenured professors damages the reputation of the academic career and the dignity of professors. | 4 | 1 | 4 | 1. Appointment to Professor Emeritus/Emerita status is a valued opportunity for transitioning of well-performing professors to retirement. 2. Attestation and annual interviews also ensure that tenured professors are constantly aware of the evaluation of their work performance and help to avoid the unpleasantness of sudden resignation resulting from underperformance. 3. Providing support to managers in solving personal, complex cases - staff and communication | 4. Development of leadership skills, regular feedback on work performance | Human Resources Office Immediate superior/ head of the research group/director/dean Human Resources Office/immediate superior (incl. appraisal interviews)/deans/directors Immediate superior/ head of the research group/director/dean | HR management HR management HR management HR management
15 | Risk 15 | II (sectoral risk) | Data Protection Officer (shall involve the head of the IT Services Office and the head of the HPC Centre) | Lack of a uniform data policy and inadequate data management diminishes the credibility and competitiveness of the university as a strategic or leading partner. | 2 | 4 | 8 | 1. Carrying out regular audits and daily monitoring of data processing and protection. 3. Regularly updating /supplementing data processing, protection and information security regulations and management systems. 5. Assessment of data processing and protection and information security risks. 7. Daily counselling and regular training of university members on data protection and information security. | 2. Carrying out additional inspections of data processing and protection. 4. Updating the data processing and protection management system. Supplementing and implementing the data processing and protection policy project. 6. Supplementing the data processing and protection and information security risk assessment (the university’s new higher level risk assessment). 8. Supplementing trainings on data protection and information security (the university’s new face-to-face and online trainings). 9. Project RAK 30 "Development of data processing principles and policies". | Data Protection Officer | Data protection and information security management; Data protection and information security management; Data protection and information security management; Data protection and information security management; Data protection and information security management;
16 | Risk 16 | II (sectoral risk) | Head of the IT Services Office (shall involve the Study Director) | Incidents related to Moodle and the study information system can prevent teaching at critical moments. | 4 | 2 | 8 | 1. A service-level agreement regarding Moodle to ensure that work can be performed according to requirements. 3. We monitor solutions in order to react as quickly as possible or proactively. 4. We have talented IT specialists. 5. We have concluded agreements with the development partners whom we can involve in case of incidents. 6. We have set a chain for incident response. 7. We develop software and make configurations in compliance with the best practice in the field of IT. 9. The data in the information systems are backed up. | 2. An SLA for the maintenance of the study information system application shall be agreed with the Office of Academic Affairs. 8. Preparation and practising of recovery plans. 10. Preparation and practising of recovery plans. | IT Services Office together with the Office of Academic Affairs | IT management; IT management; HR management IT management; IT management; IT development IT management;
17 | Risk 17 | II (sectoral risk) | Head of the IT Services Office (shall involve the Data Protection Officer and the head of the HPC Centre) | Inadequate preventive measures taken to prevent information security incidents related to important information assets of the university (the availability, integrity and confidentiality of data is not ensured) may cause a loss of availability of a business process, reputational damage, loss of important information. | 4 | 3 | 12 | 1. We develop software and make configurations in compliance with the best practice in the field of IT. 2. We monitor solutions in order to react as quickly as possible or proactively. 3. We apply reasonable security measures. 4. The information security policy has been prepared and implemented. 6. We develop software and make configurations in compliance with the best practice in the field of IT. 7. Information assets have been backed up. | 5. Implementation of the Estonian Information Security Standard. 8. Raising the awareness of the members of the university about data handling and information security. | Information Technology Services Office | Data protection and information security management; Data protection and information security management; Data protection and information security management; Data protection and information security management; IT development IT management; Data protection and information security management;
18 | Risk 18 | II (sectoral risk) | Head of IT Services Office | Some university services are unavailable or unusable due to unavailability of the computer network. | 4 | 2 | 8 | 1. Regular updating of network equipments. 3. Using backup UPSs for networking equipment. 4. The architecture and configuration of the network equipment shall be such that the failure of one device does not result in a loss of availability of the entire network. 5. Network monitoring and incident response capability. | 2. To regularly update network equipment and ensure permanent funding for that. | IT Services Office | IT management; IT management; IT management; IT management;
19 | Risk 19 | I (strategic, university-wide) | Director for Administration | Inadequate preparedness for crisis (e.g. a school shooting, a bomb attack or any other catastrophe) that has a direct impact on people’s lives, incl. poorly planned scenario and lack of awareness for quick response (bottom-up communication of information) and inability to quickly react in a crisis situation can put the lives of students and staff at risk. | 4 | 3 | 12 | 1. Regular activities preparing for crisis management and response have been carried out, but there are areas that have not been covered (e.g. technological crisis). 3. The university’s crisis management procedures, teams, roles and plans have been prepared and established, but they need to be updated and supplemented. 5. The awareness of the members of the university has been raised through corrsponding communication. 7. Crisis management and resolution trainings and exercises in key areas have been provided at the university annually, but the trainings and exercises need to be organized regularly and systematically. 9. The university has functioning technical solutions and other tools for crisis management and resolution, but there are some uncovered areas. | 2. Planning and implementation of additional activities required for the university’s preparedness for crisis management and response. Updating of various crisis management plans and schemes. 4. The university’s crisis management and response regulations need to be updated and supplemented in terms of organisational changes and additional crisis situations (e.g. war situation, technological crisis), in order to have action plans for possible different crisis situations. The crisis manager has been designated and team roles have been updated. 6. Raising the awareness of the members of the university (regarding the principles of crisis resolution) by strengthening the corresponding communication. 8. Regular and systematic planning and conduct of university’s crisis management and resolution trainings and exercises in key areas. 10. Ensuring the systemic functioning of crisis management and resolution by complementing the university’s technical solutions and other tools for crisis management and resolution. 11. Additional locking systems (doors that can be locked from the inside) for sheltering from sudden attacks. | Crisis manager; Real Estate Office | Crisis management Crisis management Crisis management Crisis management Crisis management Security services and protection of property
20 | Risk 20 | I (strategic, university-wide) | Vice-Rector for Academic Affairs | In the event of an emergency, the university will not be able to ensure full online studies over a long period of time. | 1 | 3 | 3 | 1. E-support is provided for most of the courses in Moodle; licences with the possibility to access virtual learning environments. 2. Guidelines and information materials have been prepared for e-learning and Proctorio licenses have been purchased for online examinations. 3. The teaching staff have long-term (3 semesters) online teaching experience. | 4. The possibilities for carrying out laboratory work and practical training virtually or at home. | Office of Academic Affairs; | Degree studies Degree studies Degree studies Degree studies
21 | Risk 21 | II (sectoral risk) | Chief Financial Officer | A credit risk regarding the receipt of income from students and customers | 5 | 1 | 5 | 1. The process of handling outstanding receivables (reminders + debt collection). 4. The process of handling outstanding bills (reminders + debt collection). | 2. To draw up a process guide, to describe the best practices (Finance Ofice) - what can be checked by the persons responsible. 3. Documenting, notifying of and providing training regarding the debt handling process. 5. To draw up a process guide, to describe the best practices (Finance Ofice) - what can be checked by the persons responsible. 6. Sales reports (submitted + current overview of outstanding bills). | Finance Office Dean’s offices /Finance Office Finance Office Technology Transfer Office / Finance Office | Degree studies Degree studies Provision of support services for business cooperation; Provision of support services for business cooperation;
22 | Risk 22 | II (sectoral risk) | Chief Financial Officer | The complexity and lack of operational efficiency of the procurement process puts at risk the timely execution of research projects, cooperation agreements and internal development projects and may affect the revenue received from projects/contracts. | 4 | 1 | 4 | 1. An integrated procurement process. 3. Preparation of a procurement plan (twice a year). | 2. An environment for small purchases. 4. Additional procurement specialists and or legal officers are required. 5. Reviewing of the procurement process, further optimisation, design of procurement documentation and performance analysis of procurement processes. 6. Regular trainings for contracting authorities about the procurement process. | Finance Office | Organisation of procurements Organisation of procurements Organisation of procurements Organisation of procurements
23 | Risk 23 | II (sectoral risk) | Chief Financial Officer | The overall risk of small-scale procurements, which, if not managed, can lead to claims for damages, violation or compliance notices issued to the university. | 3 | 1 | 3 | 1. The procurement assistants manually check compliance with the limits. | 2. An environment for small purchases. | Finance Office | Organisation of procurements
24 | Risk 24 | II (sectoral risk) | Chief Financial Officer | Risks of recovery of targeted funding related to ineligibility of procurements. Recovery related to procurements is usually claimed when the procurements of the purchases that received targeted funding were carried out incorrectly – this applies also with retroactive effect upon implementation of new requirements. | 5 | 2 | 10 | 1. The procurement procedure and an integrated procurement process. | 2. An environment for small purchases. 3. Additional procurement specialists and or legal officers are required. 4. Reviewing of the procurement process, further optimisation, design of procurement documentation and performance analysis of procurement processes. 5. Regular trainings for contracting authorities about the procurement process. | Finance Office | Organisation of procurements Organisation of procurements Organisation of procurements Organisation of procurements
25 | Risk 25 | I (strategic, university-wide) | Director for Administration | Permanent underfunding of the university real estate does not allow for the sustainable development of university campuses and other real estate. | 4 | 3 | 12 | 1. The new version of the Financial Regulations, which will enter into force in July of 2022, lay down that real estate shall be financed as the first priority and allows the real estate fund to be allocated before the budget is distributed between the units. 3. The annual rental income and capital budget allocated to the Real Estate Office is inadequate. | 2. Continuous and adequate funding must be agreed upon and allocated annually. 4. Preparation of the university's real estate development plan, which creates a basis for increasing real estate profitability. | Director for Administration /Finance Office Director for Administration/ Real Estate Office | Financial management Real estate and campus management
26 | Risk 26 | II (sectoral risk) | Real Estate Development Director | Power outages, network connection failures, substation maintenance or emergencies damage the reliability of the IT infrastructure, research and education infrastructures and utility systems of buildings and can cause unplanned expenses. | 5 | 2 | 10 | 1. The server rooms are partially (in the SOC and ITC buildings) supplied with UPS systems and generators. 4. Equipment insurance (the contract will expire). 6. Regular inspection and assessment of the condition of equipment and utility networks owned by the university. 8. The procedure for responding to and solving incidents defined in contracts to manage the quality of the service provided by the partners. 11. Autonomous power supply of security and access control systems for 12-24 hours. | 2. High-risk real estate related equipment, systems and rooms must be mapped by building and the need for additional equipment must be determined. 3. Generation capacity must be increased and UPSs should be employed for each piece of critical equipment. If necessary, back-up duplication in critical locations. 5. The needs to insure the equipment of the academic units must be mapped, a new procurement must be conducted and the academic units shall be informed of the insurance guarantee. 7. Supplementing the financial scheme for replacing outdated or broken equipment (cooling equipment, heating equipment). 9. Regular review of contracts. 10. It is necessary to define the criteria, when the impact of a risk increases and the risk turns into crisis and a crisis situation must be declared. 12. High-risk rooms must be mapped. Mitigation actions must be planned based on it. | Real Estate Office | Real estate and campus management Real estate and campus management Real estate and campus management Maintenance of buildings and facilities; Maintenance of buildings and facilities; Crisis management Security services and protection of property
27 | Risk 27 | II (sectoral risk) | Head of Human Resources Office | Changes in the work environment can cause employee burnout and increase of conflict situations, which lead to disruptions in the organisation of work, deterioration of the organizational climate and work performance. | 4 | 1 | 4 | 1. The services of psychologists working at the university under a contract are available to all the employees. 2. A specific occupational physician consulting service providing mental health support to employees. 3. An employee can choose a suitable form of work by agreement with his/her superior. 5. The HR Office and Office of Academic Affairs provide assistance to managers in solving conflict situations. 6. The procedure for processing appeals and complaints is laid down in the Conciliation Procedure and a procedure has been laid down for whistleblowing. | 4. Training of managers. 7. Intentional communication on the topic and training of problem recognition skills. | Human Resources Office/ heads of units | HR management HR management HR management HR management HR management HR management
28 | Risk 28 | II (sectoral risk) | Head of Human Resources Office | Discrimination among the members of the university can lead to deterioration of the organizational climate, mental health disorders of individuals and great reputational damage to the university. | 3 | 2 | 6 | 1. Defining and disclosing the principles, drawing up an action plan. 3. The Conciliation Procedure, which lays down the procedure for the resolution of cases of discrimination at the university. 5. Setting the goal of gender balance for the university as one of the key indicators in the Strategic Plan. | 2. Raising situational awareness through data disclosure and training. 4. Promoting the best practices through seminars and briefings. | Human Resources Office | HR management HR management HR management
29 | Risk 29 | II (sectoral risk) | Head of Human Resources Office | Failure to comply with the occupational safety regulations leads to occupational accidents with severe consequences, which can lead to significant loss of the ability of employees to work and cause damage to the reputation of the university. | 3 | 2 | 6 | 1. Existence and up-to-dateness of regulations, risk assessments and safety instructions. 3. Supervision and training. | 2. A digital environment for managing and using documents. 4. Digital training opportunities, reporting on completion of compulsory training. 5. Substantive organisation and quality of the work of working environment representatives. | Chief Work Environment Specialist; | HR management HR management HR management
30 | Risk 30 | II (sectoral risk) | Chief Legal Officer | Conflicts of interest in contracts may result in reputational damage or may lead to claims for damages or compliance notices issued to the university. | 4 | 1 | 4 | 1. The Procedure for Avoiding a Conflict of Interests and Preventing Corruption. 2. The course ““Preventing corruption and conflicts of interest in the public sector” available in Moodle. | 3. Additional trainings, continuous informing, to supplement ”Examples of possible conflicts of interest and a code of conduct”. 4. To review the contracting process and potential risks. | Chief Legal Officer | The support process for legal services; The support process for legal services; Internal Audit Office
31 | Risk 31 | II (sectoral risk) | Chief Financial Officer | A general decrease in purchasing power resulting from an external price shock (a sudden increase in costs makes the university suspend investments and developments or optimize more). | 3 | 3 | 9 | 1. Decentralized financial management (Financial Regulations) ensure that each unit shall achieve a budget balance and save costs, if necessary. | 2. Centrally, at the level of units and the University Board, opportunities for optimisation and cost savings and optimisation are sought through university-wide agreements (real estate, use of space, economy, etc.). 3. Analysis of the options to fix external prices. | Chief Financial Officer/ Finance Office/Academic managers Chief Financial Officer/ Finance Office | Financial management Financial management

## Risk profile - example
Risk profile symbols
Risk profile
Materialized risk
New risk
Desired situation
Current development trend
Current situation
5
4
3
2
1
1
2
3
4
5
Likelihood
Impact
Desired development trend

## Criteria
Criteria for assessing the impact of a risk
Likelihood
|  |  | 1 – will almost never occur | 2 -will seldom occur | 3 - will sometimes occur | 4 - will frequently occur | 5 - almost certain to occur
Impact | 5 | Catastrophic | Medium | Critical | Critical | Very high | Very high
| 4 | Critical | Medium | Medium | Critical | Critical | Very high
| 3 | Moderate | Minor | Medium | Critical | Critical | Critical
| 2 | Minor | Minor | Minor | Medium | Medium | Critical
| 1 | Negligible | Minor | Minor | Medium | Medium | Critical
Impact/consequence |  |  | Impact/consequence assessment criteria
Catastrophic |  | 5 | a core activity or area must be terminated at the university (bankruptcy or half of the university closed)
Critical |  | 4 | a large extent of the university’s core activities cannot be carried out during the year (significant negative impact on the university’s budget - 30-50%)
Moderate |  | 3 | significant impact, recovery from which can take 3 to 5 years (less than 25% of the budget)
Minor |  | 2 | rapid recovery, the former state can be achieved within a year by resorting to internal reserves, less than 10% of the annual budget)
Negligible |  | 1 | unpleasant, temporary, inconvenient
Likelihood |  |  | Description of likelihood
5 |  |  | The event is almost certain to occur, e.g. once a year
4 |  |  | The event occurs frequently, e.g. once every 2-3 years
3 |  |  | The event occurs sometimes, e.g. once every 4-10 years
2 |  |  | The event occurs frequently, e.g. once every 10-25 years
1 |  |  | The event occurs occurs very rarely and in exceptional circumstances, e.g. once every 25 years or less frequently

## lisa (hidden)
ÜLDJUHTIMINE | ÜLDJUHTIMINE
Kriiside juhtimine; | Kriiside juhtimine;
Eetika; | Eetika;
Riskide juhtimine; | Riskide juhtimine;
Muudatuste ja parendusvajaduste juhtimine; | Muudatuste ja parendusvajaduste juhtimine;
Kvaliteedijuhtimine; | Kvaliteedijuhtimine;
Andmekaitse ja infoturbe juhtimine; | Andmekaitse ja infoturbe juhtimine;
Taristute koordineerimine; | Taristute koordineerimine;
Finantside juhtimine; | Finantside juhtimine;
Personali juhtimine; | Personali juhtimine;
Juhtimine ja esindamine; | Juhtimine ja esindamine;
Taristute koordineerimine; | Taristute koordineerimine;
Rahvusvahelise koostöö juhtimine; | Rahvusvahelise koostöö juhtimine;
Poliitikate kujundamine; | Poliitikate kujundamine;
Siseaudit; | Siseaudit;
Strateegiline juhtimine; | Strateegiline juhtimine;
ÕPPIMINE JA ÕPETAMINE | ÕPPIMINE JA ÕPETAMINE
Õppetegevuse strateegiline juhtimine; | Õppetegevuse strateegiline juhtimine;
Olümpiaadikool; | Olümpiaadikool;
Täiendusõppe teenuse osutamine; | Täiendusõppe teenuse osutamine;
Tehnoloogiakooli teenuse osutamine; | Tehnoloogiakooli teenuse osutamine;
Eksamikooli teenuse osutamine; | Eksamikooli teenuse osutamine;
Õpiabi teenuse osutamine; | Õpiabi teenuse osutamine;
Avatud õppe teenuse osutamine; | Avatud õppe teenuse osutamine;
Tasemeõpe; | Tasemeõpe;
Õppetaristu juhtimine; | Õppetaristu juhtimine;
TEADUS JA ARENDUS | TEADUS JA ARENDUS
Teadustegevuse strateegiline juhtimine; | Teadustegevuse strateegiline juhtimine;
Doktoriõpe; | Doktoriõpe;
Muuseumi teenuse osutamine; | Muuseumi teenuse osutamine;
Kirjastuse teenuse osutamine; | Kirjastuse teenuse osutamine;
Raamatukogu teenuse osutamine; | Raamatukogu teenuse osutamine;
Teadus- ja arendustegevus: teadusprojektid; | Teadus- ja arendustegevus: teadusprojektid;
Teadustaristu juhtimine; | Teadustaristu juhtimine;
ETTEVÕTLIK ÜLIKOOL | ETTEVÕTLIK ÜLIKOOL
Ettevõtlustegevuse strateegiline juhtimine; | Ettevõtlustegevuse strateegiline juhtimine;
Ettevõtluskoostöö tugiteenuste osutamine; | Ettevõtluskoostöö tugiteenuste osutamine;
Tehnoloogiasiirde teenuste osutamine; | Tehnoloogiasiirde teenuste osutamine;
Uuseetevõtluse teenuse osutamine; | Uuseetevõtluse teenuse osutamine;
Konverentside, seminaride, töötubade korraldamine; | Konverentside, seminaride, töötubade korraldamine;
Virtuaal- ja liitreaalsuse töötubade ja koolituste korraldamine; | Virtuaal- ja liitreaalsuse töötubade ja koolituste korraldamine;
Mektory maja ruumide rentimine ja tugiteenuste pakkumine; | Mektory maja ruumide rentimine ja tugiteenuste pakkumine;
Arengufondi stipendiumite välja andmise ja annetuste vastuvõtmise koordineerimine; | Arengufondi stipendiumite välja andmise ja annetuste vastuvõtmise koordineerimine;
Vilistlassuhete koordineerimine; | Vilistlassuhete koordineerimine;
TUGITEENUSED | TUGITEENUSED
Dokumendihaldus; | Dokumendihaldus;
Asjaajamine; | Asjaajamine;
Arhiivihaldus; | Arhiivihaldus;
IT juhtimine; | IT juhtimine;
IT tugi; | IT tugi;
IT haldus; | IT haldus;
IT arendus; | IT arendus;
Kinnisvara ja linnaku juhtimine; | Kinnisvara ja linnaku juhtimine;
Hoonete ja rajatiste hooldamine; | Hoonete ja rajatiste hooldamine;
Kinnisvara ehitus- ja remont; | Kinnisvara ehitus- ja remont;
Turvateenus ja vara säilitamine; | Turvateenus ja vara säilitamine;
Kinnisvara ja rajatiste haldus; | Kinnisvara ja rajatiste haldus;
Sporditeenused; | Sporditeenused;
Hangete korraldamine; | Hangete korraldamine;
Raamatupidamine; | Raamatupidamine;
Turundus ja kommunikatsioon; | Turundus ja kommunikatsioon;
Õigusteenuste tugiprotsess;